POSEIDON v46.3

Data Migration ve Customer Onboarding Planı

Discovery → Mapping → Trial Migration → Reconciliation → Go-Live

| Konu | Kontrollü Değer |
| --- | --- |
| Amaç | Yeni şirket/filo/gemi/römorkör verisini kontrollü biçimde POSEIDON'a almak |
| Ana prensip | Import success ≠ business validation; reconciliation ve owner sign-off gerekir |
| Pilot minimum | 1 real ship + 1 real tug context'iyle prova |
| PII ilkesi | Minimum gerekli crew data; masked test data tercih edilir |
| Cutover ilkesi | Rollback/hold point olmadan production migration yapılmaz |

# 1. Onboarding fazları

| Faz | Çıktı | Exit Gate |
| --- | --- | --- |
| OB-01 Discovery | Tenant/fleet/vessel/tug/source-system inventory | Data owners assigned |
| OB-02 Data profiling | Volume/format/quality/duplicates/missing keys | Quality report approved |
| OB-03 Mapping | Source→POSEIDON entity/field/code mapping | Mapping signed |
| OB-04 Cleansing | Normalized controlled values/IDs | Reject/exception queue ready |
| OB-05 Trial import | Non-production import | Technical import pass |
| OB-06 Reconciliation | Count/hash/sample/business validation | Business sign-off |
| OB-07 Cutover rehearsal | Timing/freeze/rollback rehearsal | Go-live checklist pass |
| OB-08 Production cutover | Controlled import + delta | Operational validation |
| OB-09 Hypercare | Defects/data exceptions | Exit to BAU |

# 2. Minimum data domains

| Domain | Minimum dataset | Owner |
| --- | --- | --- |
| Tenant/Company | Legal/display name, settings, locations | Customer Admin |
| Vessel/Tug | Identity, type/subtype, flag/class, GT/kW, capabilities | Marine/Technical |
| Crew | Identity minimum, role/rank, assignment, credentials, competence | Crewing |
| Certificates/Surveys | Type, issuer, validity, survey window, evidence | Marine/Compliance |
| Equipment/PMS | Hierarchy, criticality, counters, jobs, open WO, spares | Technical |
| Safety | Open events/actions/MOC/risk templates as agreed | DPA/HSEQ |
| Documents/SMS | Controlled docs, revision, owner, effective state | Document Control |
| Tug Ops | Open jobs/history scope by customer decision | Tug Operations |

# 3. Data quality rules

Stable external/source identifier olmadan record matching yalnız ad benzerliğiyle yapılmaz.

Duplicate crew/equipment/certificate kayıtları merge edilmeden owner kararı gerekir.

Expired credential/certificate migrate edilir ama ACTIVE/VALID olarak işaretlenmez.

Historical evidence source/provenance ile korunur; doğrulanmamış belge VERIFIED olarak gelmez.

Unknown regulatory-critical data explicit UNKNOWN/REVIEW_REQUIRED olarak taşınır.

Units/timezones/codes controlled mapping olmadan normalize edilmez.

# 4. Reconciliation

| Kontrol | PASS kriteri |
| --- | --- |
| Count | Source/accepted/rejected/imported counts explainable |
| Identity | Sample vessel/tug/crew/equipment IDs correctly linked |
| Certificates | Expiry/issuer/evidence sample matches source |
| PMS | Critical equipment/counter/open WO sample matches |
| Security | Tenant/vessel scoping verified |
| Trace | Migration batch ID + source + timestamp + operator retained |
| Exceptions | All rejects have owner/disposition |
| Business | Customer data owner signs reconciliation |

# 5. Cutover runbook

T-7 days: mapping freeze, final trial, reject backlog close.

T-2 days: source delta plan, accounts/roles ready, backup and rollback assets ready.

T-0: agreed source freeze, export checksum, import, reconciliation, smoke UAT.

Go decision: Product/Customer/Engineering/QA jointly approve.

Rollback: if identity/scoping/data integrity P0 failure, stop writes and revert according to environment runbook.

T+1/T+7: hypercare data exceptions and adoption review.