## Executive Gate
POSEIDON v46.3 — Pilot, Sign-off ve Final Freeze Execution Workbook
Gate | Owner | Prerequisite | Evidence | Decision | Status | Release Impact | Note
G01 Product/BA Freeze | PO + BA Lead | v46.3 Master Spec + PRD + Trace | Signed review | APPROVE / CONDITIONAL / REJECT | OPEN | Blocks FINAL baseline | 196 screen / 2.316 field candidate
G02 Marine SME | Master/Marine Superintendent | Ship workflows | Review record | APPROVE / CONDITIONAL / REJECT | OPEN | Blocks Ship pilot | Noon/log/fuel/SOF/downtime
G03 Tug SME | Tug Master/Ops SME | Tug end-to-end | Review record | APPROVE / CONDITIONAL / REJECT | OPEN | Blocks Tug pilot | Tug lifecycle retained
G04 Regulatory | Regulatory SME | Legal register + applicability | Rule/source review | APPROVE / CONDITIONAL / REJECT | OPEN | Blocks compliance claim | P0 rules only
G05 Class/Technical | Class/Technical SME | PMS/equipment/cert/survey | Class review | APPROVE / CONDITIONAL / REJECT | OPEN | Blocks technical release | Class approval roadmap separate
G06 QA/UAT | QA Lead | Trace + E2E tests | Test report | GO / CONDITIONAL / NO-GO | OPEN | Blocks pilot exit | No unresolved P0
G07 Engineering | Tech Lead | CI build/test/DB migration | CI report | GO / CONDITIONAL / NO-GO | OPEN | Blocks code baseline | Actual environment required
G08 Ship Pilot | Pilot Owner | Real ship data | Signed UAT | GO / FIX / NO-GO | OPEN | Blocks FINAL | 1 real ship
G09 Tug Pilot | Pilot Owner | Real tug/job data | Signed UAT | GO / FIX / NO-GO | OPEN | Blocks FINAL | 1 real tug
G10 Final Freeze | Product Council | G01-G09 closed | Manifest + signatures | FINAL / CONDITIONAL | OPEN | Creates v46.3 FINAL | No fake closure

## Sign-off Matrix
Area | Required Reviewer | Scope | Review Question | Evidence Ref | Decision | Condition / Finding | Owner | Due | Status
Business Scope | PO/BA Lead | Ship + Tug + ERP boundary | Does v46.3 preserve the approved product wedge? | [5 empty] | OPEN
Ship Ops | Master/Marine SME | Noon/Daily/Fuel/SOF/Downtime | Does the workflow match actual onboard operation without duplicate burden? | [5 empty] | OPEN
Tug Ops | Tug Master/Ops SME | Job→Execution→Evidence | Are tug authority/readiness/equipment checks operationally correct? | [5 empty] | OPEN
Crew | Crewing SME | MSMD/Credentials/Competence/Rest | Does eligibility reflect actual manning/qualification decisions? | [5 empty] | OPEN
Technical/PMS | Chief Engineer/Tech Superintendent | WO/Defect/Measurement/Spare/Drydock | Does PMS support actual maintenance and critical-equipment governance? | [5 empty] | OPEN
Safety/HSEQ | DPA/HSEQ SME | RA/MOC/Barrier/Effectiveness | Does the safety model avoid generic CAPA flattening? | [5 empty] | OPEN
Regulatory | Regulatory/Legal SME | Source→Rule→Control | Are P0 applicability rules and source versions defensible? | [5 empty] | OPEN
Class/Survey | Class/RO SME | Survey/Certificate/Towing equipment | Are class-specific assumptions separated from universal rules? | [5 empty] | OPEN
Security/Data | Security/DPO | Tenant/offline/AI/privacy | Are data boundaries and AI authority acceptable? | [5 empty] | OPEN
QA | QA Lead | 196 screens / 2.316 fields | Is the controlled trace sufficient to derive complete test coverage? | [5 empty] | OPEN

## Ship Pilot
ID | Journey Step | Role | Scenario | Expected Result | Evidence | Actual Result | Defect ID | Decision | Status
SHIP-UAT-01 | Login & Today | Master | Role-aware login on pilot ship | Correct vessel context, critical exceptions, no cross-tenant data |  |  |  |  | NOT RUN
SHIP-UAT-02 | Departure readiness | Master | Prepare vessel for departure | Critical blockers visible; Why explains each state |  |  |  |  | NOT RUN
SHIP-UAT-03 | Noon Report | Chief Officer/Master | Create daily noon report offline then sync | 20+ controlled fields captured; no duplicate record; downstream reuse |  |  |  |  | NOT RUN
SHIP-UAT-04 | Deck Daily Log | OOW | Record watch/nav/port/cargo/handover | Chronological audited log; role/state controls |  |  |  |  | NOT RUN
SHIP-UAT-05 | Engine Daily Log | Engineer | Record hours/fuel/measurements/alarms/defects | Technical data links to equipment/defect/PMS |  |  |  |  | NOT RUN
SHIP-UAT-06 | Fuel/BDN/ROB | Chief Engineer | Record consumption and bunker delivery | Fuel type/quantity/BDN/ROB/evidence; applicable compliance fields activate |  |  |  |  | NOT RUN
SHIP-UAT-07 | Port Activity/SOF | Chief Officer | Record pilot/tug/berth/cargo/departure timestamps | SOF timeline produced without Port OS scope creep |  |  |  |  | NOT RUN
SHIP-UAT-08 | Operational downtime | Technical Superintendent | Create downtime linked to defect/WO | Duration/cause/operational impact/evidence trace |  |  |  |  | NOT RUN
SHIP-UAT-09 | Certificate/Survey | Superintendent | Approach survey window | Pre-survey tasks + voyage-fit + readiness impact visible |  |  |  |  | NOT RUN
SHIP-UAT-10 | Risk Assessment | Master/HSEQ | Use fleet template then customize | Initial/residual risk + controls + barriers + acknowledgements |  |  |  |  | NOT RUN
SHIP-UAT-11 | Critical PMS | Chief Engineer | Critical WO overdue / postpone request | Authority/risk/new due/readiness recalculated; no silent green |  |  |  |  | NOT RUN
SHIP-UAT-12 | Offline conflict | Master/Shore | Same material field changed offline and ashore | Conflict Center requires explicit human resolution |  |  |  |  | NOT RUN

## Tug Pilot
ID | Journey Step | Role | Scenario | Expected Result | Evidence | Actual Result | Defect ID | Decision | Status
TUG-UAT-01 | Job Intake | Tug Ops Coordinator | Create harbour-assist job | Job/context/timing/assisted vessel/required BP captured |  |  |  |  | NOT RUN
TUG-UAT-02 | Assignment | Tug Ops Coordinator | Assign own tug with overlapping candidate | Conflict detected; unsuitable candidate not silently accepted |  |  |  |  | NOT RUN
TUG-UAT-03 | Crew readiness | Tug Master/Crewing | One required credential missing/expired | Eligibility NOT_ELIGIBLE/REVIEW_REQUIRED; no false READY |  |  |  |  | NOT RUN
TUG-UAT-04 | Equipment readiness | Chief Engineer/Tug Master | ERS test failed / critical defect open | NOT_READY with exact Why; release blocked |  |  |  |  | NOT RUN
TUG-UAT-05 | BP fit | Tug Ops/Tug Master | Job requires specific BP | Certified BP source/date/verification shown; no unsafe simple sum rule |  |  |  |  | NOT RUN
TUG-UAT-06 | Towage plan | Tug Master | Define line/config/comms/contingency | Plan linked to actual tug/job/equipment |  |  |  |  | NOT RUN
TUG-UAT-07 | Risk & briefing | Tug Master/Crew | Complete job-specific RA/toolbox | Hazards/barriers/acknowledgement trace complete |  |  |  |  | NOT RUN
TUG-UAT-08 | Human release | Tug Master | Shore requests start while Tug Master rejects | System cannot bypass Tug Master |  |  |  |  | NOT RUN
TUG-UAT-09 | Execution | Tug Master | Start, suspend, resume, complete | Timeline immutable; evidence/log updated |  |  |  |  | NOT RUN
TUG-UAT-10 | Abort | Tug Master | Unsafe condition requires abort | Abort reason/evidence/escalation recorded |  |  |  |  | NOT RUN
TUG-UAT-11 | Daily log/history | Tug Master/Ops | Review completed jobs | Daily log + operation history + evidence available |  |  |  |  | NOT RUN
TUG-UAT-12 | Offline execution | Tug Master | Temporary connectivity loss | Critical workflow continues; idempotent sync on reconnect |  |  |  |  | NOT RUN

## Pilot KPI
KPI | Definition | Baseline | Target | Ship Actual | Tug Actual | Result | Owner
Task completion | Critical pilot journey completed without workaround |  | ≥95% |  |  |  | Pilot Lead
Evidence completeness | Required evidence present and traceable |  | 100% P0 |  |  |  | QA
False-green readiness | READY shown despite critical missing/failed item |  | 0 |  |  |  | QA/Regulatory
Readiness explanation accuracy | SME agrees with Why explanation |  | ≥95% |  |  |  | Marine/Tug SME
Duplicate data entry | Same operational data manually re-entered into multiple POSEIDON screens |  | ≤10% unavoidable |  |  |  | PO/BA
Offline sync success | Queued critical commands sync without duplication/loss |  | 100% |  |  |  | Engineering
Material conflict detection | Designed material conflicts surfaced for human resolution |  | 100% |  |  |  | Engineering/QA
Crew eligibility correctness | SME agrees with eligibility result |  | 100% P0 cases |  |  |  | Crewing
Critical PMS blocker detection | Critical overdue/defect state propagates to readiness |  | 100% |  |  |  | Technical
User training time | Time for role to complete core journey independently |  | ≤2 hours role onboarding |  |  |  | Pilot Lead
Critical defect escape | P0/P1 defect discovered after pilot sign-off |  | 0 P0 |  |  |  | QA

## Defect & Decision Log
ID | Date | Mode | Severity | Area | Description | Evidence | Owner | Decision | Due | Status | Retest

## Evidence Register
Evidence ID | Gate/Test ID | Object | Evidence Type | Source | Captured At | Verified By | Verification | Storage Ref | Hash/Version | Notes

## Final Freeze Decision
Criterion | Required | Actual | Status | Evidence / Ref
All G01-G09 gates closed | Yes |  | OPEN
0 unresolved P0 defects | Yes |  | OPEN
P1 defects have approved disposition | Yes |  | OPEN
Ship pilot signed | Yes |  | OPEN
Tug pilot signed | Yes |  | OPEN
Regulatory P0 reviewed | Yes |  | OPEN
Engineering CI/DB PASS | Yes |  | OPEN
196 screens / 2.316 fields trace frozen | Yes |  | OPEN
Final manifest/hash generated | Yes |  | OPEN
v46.3 FINAL decision | FINAL / CONDITIONAL / NO-GO |  | OPEN

## Dashboard
POSEIDON v46.3 — Final Freeze Readiness Dashboard
KPI | Değer | Metric | State
Executive gates closed | 0 | Product candidate | v46.3 — 196 screens / 2.316 fields
Executive gate total | 10 | Ship pilot | OPEN
Ship UAT pass | 0 | Tug pilot | OPEN
Tug UAT pass | 0 | External sign-off | OPEN
Open defects | 0 | Final freeze | NOT YET FINAL