POSEIDON v46.3

Certification, Proof & Finalization Roadmap

Class Approval • ISO • Pilot Proof • External Sign-off • Final Freeze

# 1. Amaç ve Mevcut Statü

POSEIDON v46.3, rakip benchmark sonuçları işlenmiş bir Controlled Candidate'tır. Bu belge; ürünü 'tasarlandı' durumundan 'sahada doğrulandı ve kontrollü final baseline'a alındı' durumuna geçirmek için gerekli kanıt, dış doğrulama, sertifikasyon ve release sırasını tanımlar.

Bugün verilebilecek karar: DEVELOPMENT GO. Bugün verilemeyecek karar: 'v46.3 her açıdan FINAL ve sertifikalıdır'.

| Alan | Bugünkü Durum | Final Olmak İçin |
| --- | --- | --- |
| Product/BA baseline | Hazır | PO/BA controlled sign-off |
| 196 ekran / 2.316 alan trace | Hazır | QA/BA final reconciliation |
| Prototype | Hazır | Ship + Tug UAT pass |
| Regulatory design | Hazır | P0 external regulatory/class/flag review |
| Engineering starter | Hazır | CI build/test/DB migration PASS |
| Class approval | Yok | Hedef class scheme gap + application + audit/type approval |
| ISO 27001/27701 | Yok | ISMS/PIMS scope + implementation + certification audit |
| Market proof | Pilot öncesi | 1 real ship + 1 real tug + signed UAT/case-study data |

# 2. Ürün Kanıt Hiyerarşisi

Seviye 1 — Documented: requirement, screen, field, data, API, test and regulatory trace exists.

Seviye 2 — Implemented: code builds, DB migrates, automated tests pass.

Seviye 3 — Verified: QA/SME confirms behavior against controlled acceptance criteria.

Seviye 4 — Piloted: real ship/tug users complete representative journeys with real data.

Seviye 5 — Externally Assured: applicable class/legal/security reviewers validate relevant controls.

Seviye 6 — Certified: formal certification/type approval is awarded where pursued.

# 3. PMS Class Approval Roadmap

NOZZLE karşılaştırması ürün olgunluğu açısından en büyük farklardan birinin PMS type approval olduğunu gösterdi. POSEIDON için hedef doğrudan 'sertifikalıyız' demek değil; hangi approval scheme'in gerçek ürün ve hedef müşteri için gerekli olduğunu belirleyip kontrollü başvuru yapmaktır.

| Aşama | Çıktı | Minimum İçerik | Gate |
| --- | --- | --- | --- |
| CA-01 Target Class Selection | Target class list | Pilot müşterinin class'ı + DNV/ClassNK/Türk Loydu ticari öncelik | Product Council |
| CA-02 Scheme Review | Approval requirement matrix | PMS scope, data integrity, change control, testing, cyber, backup, audit | Class/Technical SME |
| CA-03 Product Gap | Class gap backlog | Eksik function/evidence/test/procedure | PO + Engineering |
| CA-04 Evidence Pack | Controlled approval evidence | System spec, DB/API, PMS flows, test records, security/backup/change control | QA |
| CA-05 Pre-assessment | Finding list | Class reviewer feedback | Class/RO |
| CA-06 Remediation | Closed findings | Fix + regression evidence | Engineering/QA |
| CA-07 Formal Audit/Test | Audit/test report | Required product/system demonstration | Class/RO |
| CA-08 Approval | Type approval/certificate | Only after formal award may sales claim it | Authorized Class |

# 4. PMS Approval İçin Özellikle Hazır Olması Gerekenler

Equipment hierarchy and unique equipment identity.

Planned/unplanned maintenance lifecycle and recurring maintenance.

Running hours/measurement-point integrity and traceable source.

Work-order postpone/approve controls and reason/audit trail.

Critical equipment and critical task handling.

Job plan/revision history and fleet-standard job pool.

Completion evidence, verifier and immutable maintenance history.

Defect/safeguard/restriction link to equipment and readiness.

Backup/restore, user authorization, audit trail and controlled software change.

Versioned migration and regression-test evidence.

# 5. ISO 27001 / 27701 Yol Haritası

| Track | Hedef | POSEIDON Çıktısı |
| --- | --- | --- |
| ISMS Scope | Product company/cloud/dev/support boundary | Scope statement + asset/service inventory |
| Risk Management | Information-security risks | Risk register + treatment plan |
| Access | IAM/MFA/privileged access | RBAC/object-scope/SoD evidence |
| Secure SDLC | Code/dependency/secrets/release controls | SDLC policy + CI evidence |
| Supplier/Cloud | Subprocessor/provider risk | Supplier register + contracts + reviews |
| Incident | Detection/response/reporting | IR plan + exercise |
| BCP/DR | Backup/restore/RTO/RPO | DR plan + restore test |
| Privacy/PIMS | Personal data governance | Processing inventory + roles + retention + transfer controls |
| Audit | Internal audit + management review | Audit findings + management review |
| Certification | External audit | Certificate only after formal audit |

# 6. Ship Pilot — Kanıtlanacak Business Değeri

| Journey | Business Hypothesis | Success Evidence |
| --- | --- | --- |
| Departure/Readiness | Critical blocker is visible before operation | No false-green; Master agrees with Why |
| Noon/Daily Logs | One operational entry is reused across functions | Reduced duplicate entry; complete voyage/fuel context |
| Fuel/BDN/ROB | Fuel evidence supports operations and compliance | Verified BDN/ROB/consumption linkage |
| SOF/Port Activity | Timeline is defensible without becoming Port OS | Accurate timestamps and attachments |
| PMS/Defect | Critical maintenance affects operational readiness | Correct propagation to readiness |
| Certificate/Survey | Upcoming survey impacts voyage planning before expiry | Pre-survey/voyage-fit decision demonstrated |
| Offline | Core work continues during connectivity loss | No loss/duplication; conflict handled |

# 7. Tug Pilot — Kanıtlanacak Business Değeri

| Journey | Business Hypothesis | Success Evidence |
| --- | --- | --- |
| Job Intake | Towage request is structured and reusable | Complete job context |
| Assignment | Double booking/capability mismatch is caught | Conflict visible before release |
| Crew Eligibility | Statutory + competence + rest + familiarization matter together | SME agrees with status |
| Equipment Readiness | Winch/towline/ERS/FiFi/defect can block operation | NOT_READY/REVIEW_REQUIRED when required |
| BP Fit | Certified capability is visible with provenance | No unsupported arithmetic safety decision |
| Plan/RA/Briefing | Job-specific risk and barriers precede execution | Acknowledgement/evidence complete |
| Human Release | Tug Master remains final onboard authority | No shore/AI bypass |
| Execution | Suspend/abort/resume/complete are auditable | Timeline and reasons preserved |
| Offline | Towage workflow survives network loss | Idempotent sync and conflict control |

# 8. Pilot KPI Gate

| KPI | Target |
| --- | --- |
| Critical journey completion | ≥95% without workaround |
| P0 evidence completeness | 100% |
| False-green readiness | 0 |
| Readiness Why accuracy | ≥95% SME agreement |
| Crew eligibility correctness | 100% P0 test cases |
| Critical PMS blocker propagation | 100% |
| Offline command loss/duplicate | 0 |
| Material conflict detection | 100% designed cases |
| Unresolved P0 defect at exit | 0 |
| Role onboarding to core journey | ≤2 hours target |

# 9. External Sign-off Sırası

PO/BA: product scope, competitor delta and ERP boundary.

Marine SME: Ship Mode operational practicality.

Tug SME/Tug Master: towage lifecycle, equipment and authority.

Crewing SME: MSMD/credential/competence/work-rest eligibility.

Regulatory/Legal: P0 source/version/applicability logic.

Class/Technical: class-specific assumptions, PMS and towing-equipment rules.

DPA/HSEQ: safety/risk/barrier/effectiveness model.

Security/DPO: tenant, privacy, AI/data/provider boundaries.

QA: 196-screen/2,316-field trace and UAT evidence.

Engineering: CI, database migration, authorization and offline synchronization.

# 10. Final Freeze Karar Kriterleri

| Criterion | FINAL İçin |
| --- | --- |
| Product scope sign-off | CLOSED |
| Marine/Tug SME sign-off | CLOSED |
| Regulatory/Class P0 review | CLOSED |
| CI / DB engineering gate | PASS |
| Ship pilot | PASS / signed UAT |
| Tug pilot | PASS / signed UAT |
| P0 defects | 0 unresolved |
| P1 defects | Approved disposition only |
| Traceability | 196 screens / 2.316 fields frozen |
| Manifest | Final hash/version manifest generated |

# 11. 90 Günlük Uygulama Sırası

| Dönem | Odak | Çıktı |
| --- | --- | --- |
| Gün 0-15 | Internal freeze + engineering environment | PO/BA/architecture sign-off; CI/DB green |
| Gün 16-35 | Ship Ops 2.0 + PMS/Assurance priority implementation | Noon/log/fuel/pre-survey/PMS depth |
| Gün 36-50 | Tug vertical slice + risk/barrier + offline | End-to-end tug demo |
| Gün 51-60 | Regression/security/data migration rehearsal | Pre-pilot gate |
| Gün 61-75 | Real ship + tug pilot | Evidence/KPI/UAT |
| Gün 76-85 | Pilot fixes + external review closure | No P0; P1 disposition |
| Gün 86-90 | Final freeze decision | v46.3 FINAL or controlled v46.4 change set |

# 12. Nihai Karar Mantığı

Pilot/sign-off/engineering kanıtları tamamlanmadan v46.3 'FINAL' olarak etiketlenmemelidir. Bu bir eksiklik değil, ürün yönetişimi kuralıdır. Dokümantasyon ve controlled candidate hazırdır; bundan sonraki eksikler yalnız gerçek uygulama, gerçek uzman doğrulaması ve gerçek saha kanıtıyla kapanabilir.