## Backlog
ID | Type | Epic | Feature | Title | User Story | Acceptance Criteria | Screen / API | Priority | Sprint | Owner Role | Dependencies | Test Trace | Status | Pilot Gate | Estimate SP | Risk | Notes
DEV-001 | Story | E01 Platform Foundation | Repository | Repository ve branch standardını kur | Geliştirme ekibi olarak tek kontrollü kod tabanında çalışmak istiyorum. | Backend/frontend/contracts/infra/docs klasörleri oluşturulur; main/develop politikası ve PR kontrolü tanımlıdır; protected branch kuralı dokümante edilir. | Repo / CI | P0 | S0 | Engineering Lead |  | T-S0-001 | Not Started | YES | 3 | L
DEV-002 | Task | E01 Platform Foundation | CI/CD | CI pipeline iskeletini kur | Ekip olarak her PR'da build ve test görmek istiyorum. | Backend ve frontend build; unit test; lint; artifact üretimi; başarısız adım PR'ı bloklar. | CI/CD | P0 | S0 | DevOps | DEV-001 | T-S0-002 | Not Started | YES | 5 | M
DEV-003 | Story | E20 Production Hardening | Environment | DEV/TEST/UAT/PILOT ortam sözleşmesini dondur | Ekip olarak hangi ortamın ne için kullanıldığını bilmek istiyorum. | Her ortam için URL/secret/data/retention/deploy owner tanımlı; production datası DEV'e kopyalanmaz; environment promotion akışı yazılıdır. | Environment Matrix | P0 | S0 | DevOps | DEV-001 | T-S0-003 | Not Started | YES | 3 | M
DEV-004 | Story | E01 Platform Foundation | Architecture | Modular-monolith boundary ve ADR setini oluştur | Mimar olarak domain sınırlarını implementation başlamadan kontrol etmek istiyorum. | Domain modülleri, dependency yönü, event/outbox yaklaşımı, object storage, offline sync ve AI boundary ADR'ları approved durumundadır. | Architecture / ADR | P0 | S0 | Solution Architect | DEV-001 | T-S0-004 | Not Started | YES | 5 | M
DEV-005 | Story | E01 Platform Foundation | Data | Physical schema normalization planını çıkar | Backend ekibi olarak 1.900 field sözleşmesini production entity modeline bağlamak istiyorum. | Core entity listesi, PK/FK, tenancy, versioning, audit columns, evidence object refs ve migration stratejisi approved olur. | PostgreSQL Schema | P0 | S0 | Backend Lead | DEV-004 | T-S0-005 | Not Started | YES | 5 | H
DEV-006 | Story | E20 Production Hardening | Security | Threat model ve security baseline hazırla | Security owner olarak pilot öncesi kritik güvenlik sınırlarını görmek istiyorum. | Tenant isolation, authn/authz, file upload, protected reporting, secrets, audit, offline device, AI prompt/data threats kayıtlı; P0 mitigations backlog'a bağlıdır. | Security Model | P0 | S0 | Security/Architect | DEV-004 | T-S0-006 | Not Started | YES | 5 | H
DEV-007 | Story | E17 Assurance & Audit | Traceability | Pilot P0 trace paketini oluştur | PO/QA olarak her pilot journey'yi requirement-screen-api-entity-test zincirinde görmek istiyorum. | 10 pilot capability için orphan kritik öğe kalmaz; trace ID'leri backlog ve test case'lerine bağlıdır. | RTM | P0 | S0 | BA/QA Lead |  | T-S0-007 | Not Started | YES | 5 | M
DEV-008 | Story | E03 Regulatory Core | Regulatory Corpus | Pilot regulatory source ownership planı | Regulatory owner olarak pilotta hangi resmi kaynakların kullanılacağını bilmek istiyorum. | ISM/SOLAS/STCW/MLC/MARPOL/Flag/Class pilot kapsamı için source owner, version, validation status ve reviewer atanır. | Regulatory Source Register | P0 | S0 | Regulatory Lead | DEV-007 | T-S0-008 | Not Started | YES | 5 | H
DEV-009 | Story | E20 Production Hardening | Test Data | Golden pilot test datasetini hazırla | QA olarak deterministik regression testleri çalıştırmak istiyorum. | En az tanker + genel cargo/tug profile; crew/certificate/asset/defect/evidence edge cases; expected applicability/readiness outcomes kayıtlıdır. | Golden Dataset | P0 | S0 | QA Lead | DEV-005,DEV-008 | T-S0-009 | Not Started | YES | 5 | M
DEV-010 | Task | E01 Platform Foundation | Definition | Definition of Ready / Done / Release Gate dondur | Ekip olarak bir işin ne zaman başlanabilir ve tamamlanmış olduğunu aynı şekilde değerlendirmek istiyorum. | DoR/DoD; design, security, offline, audit, regulatory, docs ve test etkisini kapsar; backlog template'e uygulanır. | Team Process | P0 | S0 | Product Owner | DEV-007 | T-S0-010 | Not Started | YES | 2 | L
DEV-011 | Story | E20 Production Hardening | Observability | Observability standardını tanımla | Ops ekibi olarak pilotta hataları kök nedenle izlemek istiyorum. | Correlation/tenant/vessel/request IDs; API latency/error, sync backlog/conflict, integration retry, audit health ve data freshness metric sözleşmesi vardır. | Logging/Metrics/Tracing | P0 | S0 | DevOps | DEV-004 | T-S0-011 | Not Started | YES | 3 | M
DEV-012 | Story | E01 Platform Foundation | Kickoff | Sprint 0 exit review yap | Ekip olarak Foundation'a kontrollü geçmek istiyorum. | Architecture, data, security, trace, environments, backlog ve pilot source ownership gate'leri PASS/accepted; unresolved P0 blocker yoktur. | Sprint 0 Gate | P0 | S0 | Product Owner | DEV-001:DEV-011 | T-S0-012 | Not Started | YES | 2 | L
DEV-013 | Story | E01 Platform Foundation | Identity | OIDC login ve session context | Kullanıcı olarak kurumsal kimliğimle güvenli giriş yapmak istiyorum. | OIDC login/logout çalışır; token validation server-side; expired/invalid token state mutate etmez; correlation ID üretilir. | /api/v1/auth | P0 | S1 | Backend | DEV-002,DEV-006 | T-S1-001 | Not Started | YES | 8 | H
DEV-014 | Story | E01 Platform Foundation | Tenant | Tenant context ve izolasyon | Müşteri olarak başka tenant verisini hiçbir koşulda görmemek istiyorum. | Her query/write tenant-scoped; cross-tenant testler 403/404 policy ile bloklanır; leakage testleri PASS. | Tenant Context | P0 | S1 | Backend | DEV-013 | T-S1-002 | Not Started | YES | 8 | H
DEV-015 | Story | E01 Platform Foundation | Authorization | Role + vessel + object scope authorization | Yetkili kullanıcı olarak yalnız görev alanımdaki kayıtları görmek istiyorum. | Server-side policy role/vessel/object scope uygular; menu hiding güvenlik sınırı değildir; unauthorized state change audit edilir. | Authorization Policies | P0 | S1 | Backend | DEV-014 | T-S1-003 | Not Started | YES | 8 | H
DEV-016 | Story | E01 Platform Foundation | Audit | Immutable audit event foundation | Auditor olarak kritik değişikliklerin kim/ne zaman/neden geçmişini görmek istiyorum. | Actor, role, tenant, vessel, before/after, reason, timestamp, correlation ID kaydedilir; kritik write coverage hedefi %100. | /api/v1/audit | P0 | S1 | Backend | DEV-014,DEV-015 | T-S1-004 | Not Started | YES | 8 | H
DEV-017 | Story | E20 Production Hardening | Secrets | Secret management foundation | Ops olarak credential'ların kod/UI/log içinde bulunmamasını istiyorum. | DB/OIDC/object storage secrets vault/reference ile sağlanır; repository ve client bundle secret scan PASS. | Secrets | P0 | S1 | DevOps | DEV-003,DEV-006 | T-S1-005 | Not Started | YES | 5 | M
DEV-018 | Story | E20 Production Hardening | Files | Secure file upload pipeline | Kullanıcı olarak evidence dosyalarını güvenli yüklemek istiyorum. | Type/size/checksum validation, malware hook, signed access, tenant scope ve audit uygulanır; rejected file state mutate etmez. | /api/v1/files | P0 | S1 | Backend | DEV-017 | T-S1-006 | Not Started | YES | 8 | H
DEV-019 | Task | E20 Production Hardening | Security Test | Tenant/RBAC automated tests | QA olarak yetki regresyonunu otomatik görmek istiyorum. | Cross-tenant, role escalation, vessel scope ve protected object negatif testleri CI'da koşar. | Security Tests | P0 | S1 | QA | DEV-014,DEV-015 | T-S1-007 | Not Started | YES | 5 | H
DEV-020 | Story | E02 Vessel & Fleet Context | Vessel | Vessel master ve regulatory profile | DPA olarak pilot geminin tek kontrollü profile sahip olmasını istiyorum. | IMO no, flag, class, ship type, GT, build/trading/cargo context versioned kaydedilir; provenance/freshness görünür. | fleet-vessels / /api/v1/vessels | P0 | S2 | Backend+Frontend | DEV-005,DEV-014 | T-S2-001 | Not Started | YES | 8 | M
DEV-021 | Story | E02 Vessel & Fleet Context | Live Context | Global vessel/role context | Kullanıcı olarak hangi gemi ve rol bağlamında çalıştığımı her ekranda görmek istiyorum. | Context topbar görünür; vessel switch authorization check yapar; unsaved critical form context change'i uyarır. | UI Shell | P0 | S2 | Frontend | DEV-015,DEV-020 | T-S2-002 | Not Started | YES | 5 | M
DEV-022 | Story | E01 Platform Foundation | Navigation | Role-first navigation shell | Master/Chief Engineer/Crew olarak yalnız günlük görevime uygun menüyü görmek istiyorum. | Role lens ile sade menü gelir; Full product search authorized power users'a açıktır; 172 ekran düz menü olarak gösterilmez. | App Shell | P0 | S2 | Frontend | DEV-015,DEV-021 | T-S2-003 | Not Started | YES | 8 | M
DEV-023 | Story | E15 Search & Notifications | Today | POSEIDON Today shell | Kullanıcı olarak bugünkü kritik işleri tek listede görmek istiyorum. | Exception cards priority/source/Why/owner/next action taşır; loading/empty/error/offline states deterministiktir. | poseidon-today / /api/v1/today | P0 | S2 | Frontend+Backend | DEV-021,DEV-022 | T-S2-004 | Not Started | YES | 8 | M
DEV-024 | Story | E05 Human Decision & Workflow | Why | Why Engine temel kontratı | Kullanıcı olarak bir state'in neden oluştuğunu görmek istiyorum. | Critical state için source/reason/input freshness/blocker listesi döner; unauthorized source detail sızmaz. | why-engine / /api/v1/why | P0 | S2 | Backend | DEV-016,DEV-023 | T-S2-005 | Not Started | YES | 8 | M
DEV-025 | Task | E20 Production Hardening | Accessibility | UI accessibility baseline | Kullanıcı olarak renk dışında metin/state ile bilgi almak istiyorum. | Keyboard focus, contrast, status text/icon, responsive breakpoints ve form error semantics temel shell'de PASS. | Design System | P1 | S2 | Frontend/UX | DEV-022 | T-S2-006 | Not Started | NO | 5 | L
DEV-026 | Story | E03 Regulatory Core | Requirement | Requirement/source/version entity | Regulatory admin olarak requirement'ları source/version lifecycle ile yönetmek istiyorum. | Draft/adopted/future/in-force/superseded ayrımı vardır; current source silent overwrite edilmez. | requirement-master / /api/v1/requirements | P0 | S3 | Backend | DEV-005,DEV-008 | T-S3-001 | Not Started | YES | 8 | H
DEV-027 | Story | E03 Regulatory Core | Applicability | Applicability evaluation engine v1 | DPA olarak pilot gemiye hangi requirement'ın neden uygulandığını görmek istiyorum. | Flag/type/GT/build/cargo/trading context predicate'leri versioned; result APPLICABLE/NOT_APPLICABLE/REVIEW_REQUIRED + reason döner. | applicability / /api/v1/applicability/evaluate | P0 | S3 | Backend | DEV-020,DEV-026 | T-S3-002 | Not Started | YES | 13 | H
DEV-028 | Story | E04 Control & Evidence | Control | Operational Control entity | Regulatory/safety admin olarak requirement'ı operasyonel kontrole bağlamak istiyorum. | Owner/frequency/evidence rule/verification rule/state ve requirement links kaydedilir; orphan critical control raporlanır. | /api/v1/controls | P0 | S3 | Backend | DEV-026,DEV-027 | T-S3-003 | Not Started | YES | 8 | M
DEV-029 | Story | E04 Control & Evidence | Evidence | Evidence graph foundation | Kullanıcı olarak bir kanıtı birden fazla gereksinimi desteklemek için kullanmak istiyorum. | Evidence immutable metadata/checksum/provenance ile kaydedilir; many-to-many links; stale/expired/superseded durumu görünür. | /api/v1/evidence | P0 | S3 | Backend | DEV-018,DEV-028 | T-S3-004 | Not Started | YES | 13 | H
DEV-030 | Story | E04 Control & Evidence | Verification | Verification record ve gate | Verifier olarak kanıtı kabul/reject etmek ve gerekçe bırakmak istiyorum. | Verifier authorization + separation-of-duties; PENDING/VERIFIED/REJECTED/EXPIRED/SUPERSEDED; evidence existence alone state'i kapatmaz. | /api/v1/verifications | P0 | S3 | Backend | DEV-015,DEV-029 | T-S3-005 | Not Started | YES | 8 | H
DEV-031 | Story | E05 Human Decision & Workflow | Decision | Authorized Human Decision foundation | Master/DPA olarak kritik kararı gerekçesiyle vermek istiyorum. | Authorized role + context + reason + decision lineage kaydedilir; AI veya generic admin final decision oluşturamaz. | /api/v1/decisions | P0 | S3 | Backend | DEV-030 | T-S3-006 | Not Started | YES | 8 | H
DEV-032 | Task | E17 Assurance & Audit | Trace UI | Requirement-to-decision trace görünümü | Auditor olarak requirement'tan karara kadar tek trace görmek istiyorum. | Requirement→control→evidence→verification→decision state ve timestamps source-grounded drill-down ile görünür. | audit-ready | P0 | S3 | Frontend | DEV-027:DEV-031 | T-S3-007 | Not Started | YES | 8 | M
DEV-033 | Story | E13 Offline & Sync | Queue | Durable offline queue | Gemide bağlantı yokken supported kayıtları kaybetmeden yapmak istiyorum. | Client UUID/base version/timestamp ile queue restart sonrası korunur; encrypted local storage; pending state görünür. | Mobile/Offline Core | P0 | S4 | Frontend | DEV-021,DEV-029 | T-S4-001 | Not Started | YES | 13 | H
DEV-034 | Story | E13 Offline & Sync | Sync | Idempotent sync API | Sistem olarak reconnect sonrası duplicate oluşturmadan kayıtları göndermek istiyorum. | Idempotency key + expected version; retry duplicate critical state yaratmaz; server authoritative result döner. | /api/v1/sync/operations | P0 | S4 | Backend | DEV-033 | T-S4-002 | Not Started | YES | 13 | H
DEV-035 | Story | E13 Offline & Sync | Conflict | Material conflict center | Yetkili kullanıcı olarak kritik conflict'i açıkça çözmek istiyorum. | High-risk conflict auto overwrite olmaz; before/local/server context gösterilir; human resolution audit edilir. | offline-conflict-center / /api/v1/sync/conflicts | P0 | S4 | Full Stack | DEV-034,DEV-016 | T-S4-003 | Not Started | YES | 8 | H
DEV-036 | Story | E15 Search & Notifications | Notification | Notification/escalation engine v1 | Owner olarak kritik deadline ve exception'ları zamanında almak istiyorum. | Severity/due/state trigger; dedupe; acknowledgement/escalation audit; mandatory critical route user preference ile susturulamaz. | notification-escalation | P1 | S4 | Backend | DEV-016 | T-S4-004 | Not Started | YES | 8 | M
DEV-037 | Story | E20 Production Hardening | Observability | Health dashboard v1 | Ops olarak API, sync ve audit sağlığını ayırarak görmek istiyorum. | API errors/latency, sync backlog/conflict, audit writer, file service ve data freshness metrikleri görünür. | system-health | P0 | S4 | DevOps+Frontend | DEV-011,DEV-034 | T-S4-005 | Not Started | YES | 8 | M
DEV-038 | Task | E13 Offline & Sync | Chaos | Offline chaos regression pack | QA olarak network loss/duplicate/clock drift/attachment retry'ı otomatik test etmek istiyorum. | Network drop/reconnect, duplicate request, stale base version, attachment retry, conflict paths otomasyonda PASS. | Offline Tests | P0 | S4 | QA | DEV-033:DEV-035 | T-S4-006 | Not Started | YES | 8 | H
DEV-039 | Story | E02 Vessel & Fleet Context | Onboarding | Pilot vessel onboarding wizard | Implementation admin olarak pilot gemiyi kontrollü şekilde sisteme almak istiyorum. | Identity/profile/flag/class/type/GT/cargo/trading context completeness kontrolü; missing critical field REVIEW_REQUIRED üretir. | fleet-vessels | P0 | S5 | Full Stack | DEV-020,DEV-027 | T-S5-001 | Not Started | YES | 8 | M
DEV-040 | Story | E03 Regulatory Core | Applicability UI | Applicability reason review | Regulatory owner olarak otomatik applicability sonucunu incelemek istiyorum. | Rule version, inputs, source, result, reviewer state görünür; manual override controlled reason + audit gerektirir. | applicability | P0 | S5 | Full Stack | DEV-027,DEV-039 | T-S5-002 | Not Started | YES | 8 | H
DEV-041 | Story | E04 Control & Evidence | Control generation | Applicable controls oluştur | DPA olarak pilot gemi için gereken control/evidence planını görmek istiyorum. | Applicable requirement'lar kontrollere bağlanır; owner/frequency/evidence/verification fields vardır; orphan critical requirement=0 hedeflenir. | control-library | P0 | S5 | Backend | DEV-028,DEV-040 | T-S5-003 | Not Started | YES | 8 | H
DEV-042 | Story | E02 Vessel & Fleet Context | Passport | Digital Compliance Passport pilot view | DPA/Auditor olarak geminin requirement/certificate/evidence durumunu tek yerde görmek istiyorum. | Current applicable requirements, certificates, evidence completeness, blockers ve source freshness drill-down ile görünür. | digital-compliance-passport | P1 | S5 | Frontend | DEV-032,DEV-041 | T-S5-004 | Not Started | YES | 8 | M
DEV-043 | Story | E17 Assurance & Audit | Certificates | Certificate Intelligence Center | DPA/Crewing olarak yaklaşan expiry ve survey window'u tek listede görmek istiyorum. | VALID/DUE/SURVEY_WINDOW/EXPIRED/REVIEW_REQUIRED state; issuer/source/verification; vessel/crew scope filtreleri. | certificate-command-center | P0 | S6 | Full Stack | DEV-020,DEV-030 | T-S6-001 | Not Started | YES | 13 | M
DEV-044 | Story | E17 Assurance & Audit | Renewal | Renewal workflow v1 | Certificate owner olarak yenilemeyi survey/application/yeni belge/verification adımlarıyla yönetmek istiyorum. | Owner/actions/due/survey window/new certificate evidence/verification; old certificate superseded history korunur. | renewal-workflow | P1 | S6 | Full Stack | DEV-043 | T-S6-002 | Not Started | YES | 8 | M
DEV-045 | Story | E19 Fleet Intelligence | AI OCR | Certificate OCR assist | Kullanıcı olarak sertifika foto/PDF'inden alanları otomatik taslak almak istiyorum. | Belge tipi/no/issuer/dates/vessel-person çıkarılır; confidence gösterilir; low confidence vurgulanır; user confirm olmadan save/state mutation yok. | certificate-command-center / AI extraction | P0 | S6 | AI+Full Stack | DEV-018,DEV-043 | T-S6-003 | Not Started | YES | 13 | H
DEV-046 | Task | E19 Fleet Intelligence | AI Evaluation | OCR golden-set evaluation | QA olarak extraction kalitesini kontrollü test etmek istiyorum. | Masked sample set; field-level accuracy/correction rate ölçülür; critical field hallucination/authority bypass yok; model/prompt version loglanır. | AI Evaluation | P0 | S6 | AI+QA | DEV-045,DEV-009 | T-S6-004 | Not Started | YES | 8 | H
DEV-047 | Story | E06 Crew & Competence | Roster | Crew roster + profile | Master/Crewing olarak onboard/planned crew'yu görmek istiyorum. | Person/assignment/rank/capacity/period scoped; privacy masking and vessel scope; offline supported read/capture as defined. | crew-roster / crew-profile | P0 | S7 | Full Stack | DEV-020,DEV-015 | T-S7-001 | Not Started | YES | 8 | M
DEV-048 | Story | E06 Crew & Competence | Credentials | Crew certificates & endorsements | Crewing olarak STCW/medical/endorsement kayıtlarını doğrulanmış şekilde tutmak istiyorum. | Issue/expiry/issuer/endorsement/vessel scope/verification; expired/unverified positive eligibility üretmez. | crew-certificates | P0 | S7 | Full Stack | DEV-047,DEV-030 | T-S7-002 | Not Started | YES | 8 | H
DEV-049 | Story | E06 Crew & Competence | Competence | Training-position/competence gate | Crewing olarak pozisyon ve vessel type'a göre gerekli competence/training gap'lerini görmek istiyorum. | Requirement type, mandatory, validity, vessel/cargo scope, competence/familiarization links; missing gap reason listesinde görünür. | training-position-matrix | P0 | S7 | Full Stack | DEV-048,DEV-027 | T-S7-003 | Not Started | YES | 8 | H
DEV-050 | Story | E06 Crew & Competence | Safe Manning | Crew eligibility + Safe Manning evaluation | Master olarak atamanın ve mevcut manning'in uygunluğunu açıklanabilir şekilde görmek istiyorum. | Credential+competence+familiarization+work/rest+MSMD constraints değerlendirilir; ELIGIBLE/ATTENTION/NOT_ELIGIBLE/REVIEW_REQUIRED + reason. | safe-manning / /api/v1/vessels/{id}/safe-manning/evaluate | P0 | S7 | Backend+Frontend | DEV-047:DEV-049 | T-S7-004 | Not Started | YES | 13 | H
DEV-051 | Task | E06 Crew & Competence | Privacy | Crew privacy access regression | Privacy owner olarak crew personal data'nın gereksiz rollere sızmamasını istiyorum. | Purpose/scope masking tests; protected fields generic export/search'ta görünmez; access events audit edilir. | Crew Security Tests | P0 | S7 | QA/Security | DEV-047,DEV-048 | T-S7-005 | Not Started | YES | 5 | H
DEV-052 | Story | E07 Technical Safety | Equipment | Equipment hierarchy pilot | Chief Engineer olarak asset/system/equipment hiyerarşisini yönetmek istiyorum. | Criticality, maker/model/serial/location/parent-child versioned; vessel scope; invalid cycle bloklanır. | equipment-hierarchy | P0 | S8 | Full Stack | DEV-020 | T-S8-001 | Not Started | YES | 8 | M
DEV-053 | Story | E07 Technical Safety | PMS | Maintenance plan + trigger | Chief Engineer olarak calendar/meter/condition tetikli bakım planı oluşturmak istiyorum. | Job/interval/meter/condition/criticality/owner; due calculation deterministic; invalid postponement blocked/audited. | maintenance-plan | P0 | S8 | Backend+Frontend | DEV-052 | T-S8-002 | Not Started | YES | 13 | H
DEV-054 | Story | E07 Technical Safety | Work Order | Work order execution + evidence | Crew/Engineer olarak işi uygulayıp required evidence ile göndermek istiyorum. | RELEASED→IN_PROGRESS→EVIDENCE_SUBMITTED; readings/spares/photo/doc; required evidence yoksa verification/close olmaz. | work-order-center / work-order-detail | P0 | S8 | Full Stack | DEV-029,DEV-053 | T-S8-003 | Not Started | YES | 13 | H
DEV-055 | Story | E07 Technical Safety | Defect | Critical defect lifecycle | Chief Engineer olarak kritik arızayı safeguard ve restriction ile yönetmek istiyorum. | Detect→Assess→Safeguard→Action→Verify→Effectiveness; critical defect without safeguard cannot close; temporary measure expiry monitored. | technical-readiness / defect APIs | P0 | S8 | Full Stack | DEV-030,DEV-052 | T-S8-004 | Not Started | YES | 13 | H
DEV-056 | Story | E07 Technical Safety | Readiness | PMS Command Center | Chief Engineer olarak overdue critical jobs/defects/spare gaps'i tek yerde görmek istiyorum. | Critical overdue/open WO/condition alert/spare gap ve Why drill-down; healthy items quiet; stale data visible. | pms-command-center | P0 | S8 | Frontend+Backend | DEV-053:DEV-055 | T-S8-005 | Not Started | YES | 8 | M
DEV-057 | Task | E07 Technical Safety | Offline PMS | WO offline execution | Engineer olarak bağlantı yokken bakım evidence'ını kaybetmeden toplamak istiyorum. | WO context prefetched; evidence queue durable; reconnect sync idempotent; material field conflict center'a gider. | mobile-task-center / work-order-detail | P0 | S8 | Full Stack | DEV-033:DEV-035,DEV-054 | T-S8-006 | Not Started | YES | 8 | H
DEV-058 | Story | E08 Operations & Readiness | Departure | Departure readiness aggregation | Master olarak kalkıştan önce crew/technical/statutory/emergency blocker'ları görmek istiyorum. | Readiness state READY/CONDITIONAL/NOT_READY/REVIEW_REQUIRED; critical blocker average score ile maskelenmez; Why listesi vardır. | departure-signoff | P0 | S9 | Backend+Frontend | DEV-042,DEV-050,DEV-055 | T-S9-001 | Not Started | YES | 13 | H
DEV-059 | Story | E05 Human Decision & Workflow | Master Signoff | Master departure decision | Master olarak evidence ve safeguards'i görüp nihai kararı vermek istiyorum. | Only authorized Master; decision/reason/time/context stored immutable lineage; AI/admin cannot sign; changed material input makes previous decision STALE. | departure-signoff / /api/v1/decisions | P0 | S9 | Full Stack | DEV-031,DEV-058 | T-S9-002 | Not Started | YES | 8 | H
DEV-060 | Story | E10 Safety Events & Learning | Event | Safety event/near-miss capture | Crew olarak olay veya near miss'i hızlı bildirmek istiyorum. | Type/date/vessel/context/description/evidence; immediate action; protected mode separate where needed; offline capture supported. | events-learning / /api/v1/safety-events | P0 | S9 | Full Stack | DEV-033,DEV-029 | T-S9-003 | Not Started | YES | 8 | M
DEV-061 | Story | E10 Safety Events & Learning | Investigation | Event analysis → barrier/action → effectiveness | DPA olarak olayın kontrol/aksiyon/etkinlik zincirini yönetmek istiyorum. | Contributing factors/root cause/barrier/action/owner/due/evidence/verification/effectiveness; Closed != Effective. | events-learning | P0 | S9 | Full Stack | DEV-060,DEV-030 | T-S9-004 | Not Started | YES | 13 | H
DEV-062 | Story | E19 Fleet Intelligence | Voice AI | Voice-to-event draft | Crew/Master olarak kısa Türkçe sesli nottan yapılandırılmış olay taslağı almak istiyorum. | Transcription/draft source trace + confidence; user edit/confirm required; model/prompt/version logged; no autonomous submission/closure. | events-learning / AI draft | P1 | S9 | AI+Frontend | DEV-060 | T-S9-005 | Not Started | YES | 8 | M
DEV-063 | Task | E19 Fleet Intelligence | Voice AI Test | Voice draft evaluation | QA olarak gerçekçi denizcilik notlarında taslak kullanılabilirliğini ölçmek istiyorum. | Masked test set; field completeness/correction/usability measured; critical fabricated fact=0 in golden set; user rejection is logged. | AI Evaluation | P1 | S9 | AI+QA | DEV-062,DEV-009 | T-S9-006 | Not Started | YES | 5 | M
DEV-064 | Story | E17 Assurance & Audit | Audit Pack | Pilot audit-ready pack | Auditor olarak seçili requirement için kanıtı dakikalar içinde bulmak istiyorum. | Requirement/control/evidence/verification/decision/history export/view; superseded evidence trace retained; unauthorized protected data excluded. | audit-ready | P0 | S10 | Full Stack | DEV-032,DEV-043,DEV-061 | T-S10-001 | Not Started | YES | 8 | M
DEV-065 | Story | E04 Control & Evidence | Data Quality | Evidence/Data quality signals | DPA olarak missing/stale/conflicting/unverified/orphan durumlarını görmek istiyorum. | Material data quality state readiness'i degrade eder; source/provenance/freshness visible; false green blocked. | data-trust-center | P0 | S10 | Backend+Frontend | DEV-029,DEV-037 | T-S10-002 | Not Started | YES | 8 | H
DEV-066 | Task | E13 Offline & Sync | Pilot Offline | Full pilot offline journey | Pilot ekibi olarak cert/event/WO kayıtlarında bağlantı kesintisini doğrulamak istiyorum. | At least three pilot workflows pass network loss/reconnect/duplicate/conflict/attachment retry with no data loss. | mobile-task-center / offline-conflict-center | P0 | S10 | QA+Full Stack | DEV-038,DEV-045,DEV-057,DEV-060 | T-S10-003 | Not Started | YES | 13 | H
DEV-067 | Task | E20 Production Hardening | Performance | Pilot workload performance baseline | Ekip olarak pilot yükünde günlük yüzeylerin hızlı çalıştığını doğrulamak istiyorum. | Today/readiness/audit queries bounded; agreed p95 envelope recorded; slow query traces actionable. | Performance Tests | P1 | S10 | QA/Backend | DEV-023,DEV-058,DEV-064 | T-S10-004 | Not Started | YES | 8 | M
DEV-068 | Task | E20 Production Hardening | Security | Pre-pilot security gate | Product owner olarak kritik güvenlik bulgusu olmadan pilotu açmak istiyorum. | RBAC/tenant/file upload/privilege escalation/secret scans pass; unresolved critical/high=0 for pilot scope. | Security Gate | P0 | S10 | Security/QA | DEV-019,DEV-051,DEV-018 | T-S10-005 | Not Started | YES | 8 | H
DEV-069 | Story | E14 Integration & Migration | Import | Pilot data import templates | Implementation ekibi olarak vessel/crew/certificate/equipment verisini kontrollü taşımak istiyorum. | Template mapping + validation + reject report + provenance; duplicate/key rules; no direct bypass of domain validation. | Import/Migration | P0 | S11 | Backend+Implementation | DEV-020,DEV-047,DEV-052 | T-S11-001 | Not Started | YES | 8 | M
DEV-070 | Story | E14 Integration & Migration | Reconciliation | Pilot data reconciliation report | Müşteri olarak aktarılan verinin doğruluğunu örnekleyip onaylamak istiyorum. | Source count/accepted/rejected/duplicate/missing critical list; owner sign-off before pilot start. | Data Reconciliation | P0 | S11 | Implementation+QA | DEV-069 | T-S11-002 | Not Started | YES | 5 | M
DEV-071 | Task | E20 Production Hardening | Backup/DR | Pilot backup & restore rehearsal | Ops olarak pilot öncesi geri yüklemenin gerçekten çalıştığını görmek istiyorum. | DB + object evidence backup alınır; restore test edilir; RPO/RTO measured; rollback procedure signed. | DR Runbook | P0 | S11 | DevOps | DEV-003,DEV-018 | T-S11-003 | Not Started | YES | 8 | H
DEV-072 | Story | E15 Search & Notifications | Pilot Telemetry | Pilot metrics instrumentation | PO olarak task success/adoption/evidence search/offline/AI correction metriklerini görmek istiyorum. | Privacy-safe event schema; role adoption, journey completion, AI correction, sync conflicts, evidence search time ölçülebilir. | Pilot Metrics | P0 | S11 | Product Analytics | DEV-023,DEV-045,DEV-062 | T-S11-004 | Not Started | YES | 5 | M
DEV-073 | Task | E17 Assurance & Audit | Regulatory Gate | Pilot regulatory SME review | PO olarak pilot applicability/control setinin uzman tarafından doğrulandığını bilmek istiyorum. | Pilot vessel profile için authoritative source/version reviewer sign-off; open ambiguity REVIEW_REQUIRED ve tracked issue olarak kalır. | Regulatory Review | P0 | S11 | Regulatory Lead | DEV-008,DEV-040,DEV-041 | T-S11-005 | Not Started | YES | 8 | H
DEV-074 | Task | E20 Production Hardening | UAT | Pre-pilot role UAT | Master/DPA/C/E/Crew olarak ana görevleri yardımsız tamamlamak istiyorum. | Critical role journeys agreed threshold'u geçer; blocker UX issue kalmaz; design conformance reviewed. | UAT | P0 | S11 | QA/UX/Product | DEV-023,DEV-043,DEV-050,DEV-056,DEV-059,DEV-060 | T-S11-006 | Not Started | YES | 8 | M
DEV-075 | Task | E20 Production Hardening | Pilot Gate | Pilot go/no-go review | Steering group olarak kontrollü pilot başlangıç kararı vermek istiyorum. | Security/regulatory/offline/DR/UAT/data/trace gates PASS; unresolved P0=0; pilot support/on-call ready. | Pilot Gate | P0 | S11 | Product Owner | DEV-068:DEV-074 | T-S11-007 | Not Started | YES | 3 | L
DEV-076 | Task | E19 Fleet Intelligence | Pilot Week 1 | Pilot Week 1 - Today, vessel, certificates, crew | Pilot ekip olarak günlük kullanım ve ilk canlı exception/evidence trace'i doğrulamak istiyoruz. | Daily feedback captured; first live trace demonstrated; onboarding/certificate/crew P0 issues triaged same day. | Pilot | P0 | PILOT-W1 | Product+Customer Success | DEV-075 | T-P1 | Not Started | YES | 5 | M
DEV-077 | Task | E07 Technical Safety | Pilot Week 2 | Pilot Week 2 - PMS, defects, departure, offline | Pilot ekip olarak gemi teknik ve onboard akışlarını gerçek işte doğrulamak istiyoruz. | At least one WO, one defect/safeguard, one departure review, one offline/reconnect flow completed with audit trace. | Pilot | P0 | PILOT-W2 | Product+Pilot Team | DEV-076 | T-P2 | Not Started | YES | 5 | H
DEV-078 | Task | E10 Safety Events & Learning | Pilot Week 3 | Pilot Week 3 - safety event, evidence, AI assist | Pilot ekip olarak olay/evidence ve AI assist'in güvenli kullanımını ölçmek istiyoruz. | At least one event flow; audit pack retrieval; OCR/voice correction metrics; no AI authority bypass. | Pilot | P0 | PILOT-W3 | Product+Pilot Team | DEV-077 | T-P3 | Not Started | YES | 5 | M
DEV-079 | Task | E17 Assurance & Audit | Pilot Week 4 | Pilot Week 4 - assurance/UAT/value readout | Yönetim olarak pilotun devam/genişleme kararını kanıtla vermek istiyoruz. | Before/after metrics; unresolved defects severity; UAT signoff; value report; go/no-go/expand decision recorded. | Pilot | P0 | PILOT-W4 | Product Owner | DEV-078 | T-P4 | Not Started | YES | 5 | M
DEV-080 | Story | E21 Tug Operations | Tug Context | Römorkör mode context ve profile root | Römorkör Operasyon Sorumlusu olarak römorkörün operasyonel profile/role contextini görmek istiyorum. | Tug profile bollard pull/type/equipment context + role lens; Ship Mode screens remain hidden unless cross-mode role. | tug-command / /api/v1/tug-command | P0 | S5 | Full Stack | DEV-020,DEV-022 | T-TUG-001 | Not Started | YES | 8 | M | v46.2
DEV-081 | Story | E21 Tug Operations | Job Intake | Römorkör iş talebi kaydı | Operasyon sorumlusu olarak yeni römorkaj işini assisted vessel, zaman, alan, BP ve özel gereksinimle açmak istiyorum. | Job ID; assisted vessel; job type; time window; area; required tug count/BP; priority; owner; audited create. | tug-job-intake / /api/v1/tug-jobs | P0 | S6 | Full Stack | DEV-080 | T-TUG-002 | Not Started | YES | 8 | M | v46.2
DEV-082 | Story | E21 Tug Operations | Job Board | Kısa ve sık römorkör iş panosu | Operasyon sorumlusu olarak gün içi işleri zaman ve readiness ile görmek istiyorum. | Job board shows planned window, assigned tugs, BP, readiness, conflict, priority and next action. | tug-job-board | P0 | S6 | Frontend+Backend | DEV-081 | T-TUG-003 | Not Started | YES | 8 | M | v46.2
DEV-083 | Story | E21 Tug Operations | Assignment | Römorkör atama ve çakışma kontrolü | Operasyon sorumlusu olarak işi uygun römorköre atarken overlap, crew, equipment, PMS ve certificate durumunu görmek istiyorum. | Assignment checks time overlap + crew/equipment/PMS/cert; shore proposes; Master/Tug Master acknowledgement preserved. | tug-assignment / /api/v1/tug-assignments | P0 | S7 | Full Stack | DEV-050,DEV-055,DEV-082 | T-TUG-004 | Not Started | YES | 13 | H | v46.2
DEV-084 | Story | E21 Tug Operations | Readiness | Römorkör operasyon readiness gate | Master/Tug Master olarak işe çıkmadan crew, equipment, PMS, certificate, comms, weather ve BP margin görmek istiyorum. | READY/CONDITIONAL/NOT_READY/REVIEW_REQUIRED; critical blocker cannot be averaged; Master decision and reason retained. | tug-readiness / /api/v1/tug-readiness | P0 | S7 | Full Stack | DEV-083 | T-TUG-005 | Not Started | YES | 13 | H | v46.2
DEV-085 | Story | E21 Tug Operations | Equipment Readiness | Tow equipment readiness | Chief Engineer olarak winch, tow hook, towline, emergency release, FiFi ve critical defects durumunu görmek istiyorum. | SWL/test/condition/PMS/certificate evidence; NOT_READY on critical failure; evidence/verification trace. | tug-equipment-readiness | P0 | S7 | Full Stack | DEV-052,DEV-055 | T-TUG-006 | Not Started | YES | 8 | H | v46.2
DEV-086 | Story | E21 Tug Operations | Crew Readiness | Römorkör crew/towage competence readiness | Master/Crewing olarak minimum manning, credential, towage competence, familiarization ve work/rest durumunu görmek istiyorum. | Shared crew engine + tug-specific towage competence; positive readiness blocked by missing/unverified credential/competence. | tug-crew-readiness | P0 | S7 | Full Stack | DEV-048,DEV-050 | T-TUG-007 | Not Started | YES | 8 | H | v46.2
DEV-087 | Story | E21 Tug Operations | Towage Plan | Römorkaj operasyon planı | Master/Tug Master olarak çekme konfigürasyonu, towline, BP, limitler, communication ve contingency planını hazırlamak istiyorum. | Plan has tug roles, configuration, limits, communication, emergency release, contingency, snap-back controls and approval state. | towage-plan / /api/v1/towage-plans | P0 | S8 | Full Stack | DEV-084,DEV-085 | T-TUG-008 | Not Started | YES | 13 | H | v46.2
DEV-088 | Story | E21 Tug Operations | Risk & Briefing | Römorkaj risk ve brifing | Master/Tug Master olarak weather/current/visibility/hazards/barriers/stop-work koşullarını ekip ile teyit etmek istiyorum. | Risk state + preventive/mitigating barriers + stop-work + emergency + participants acknowledgement; incomplete briefing blocks READY. | towage-risk-briefing | P0 | S8 | Full Stack | DEV-087 | T-TUG-009 | Not Started | YES | 8 | H | v46.2
DEV-089 | Story | E21 Tug Operations | Execution | Römorkaj operasyon yürütme | Master/Tug Master olarak start/suspend/resume/abort/complete ve operasyon kanıtını kaydetmek istiyorum. | Timeline, towline times, max load, comms, weather, events, Master decision, evidence, verification; shore/AI cannot start/abort operation. | towage-execution / /api/v1/towage-executions | P0 | S9 | Full Stack | DEV-088,DEV-031 | T-TUG-010 | Not Started | YES | 13 | H | v46.2
DEV-090 | Story | E21 Tug Operations | Daily Log | Römorkör günlük defteri | Master olarak vardiya/gün sonunda iş, runtime, fuel, defect, safety event ve özet kaydı yapmak istiyorum. | Daily log works offline; job links and meter values reconcile; Master review + sync state visible. | tug-daily-log | P1 | S9 | Full Stack | DEV-033,DEV-089 | T-TUG-011 | Not Started | YES | 8 | M | v46.2
DEV-091 | Story | E21 Tug Operations | History | Römorkör operasyon geçmişi | Operasyon/DPA olarak geçmiş işi gemi, tip, süre, Master, sonuç ve evidence durumuyla aramak istiyorum. | History filterable by tug/job/vessel/date/outcome; no silent deletion; trace to evidence/event. | tug-operation-history | P1 | S10 | Full Stack | DEV-089 | T-TUG-012 | Not Started | YES | 5 | M | v46.2
DEV-092 | Story | E21 Tug Operations | Offline | Römorkör job/briefing/execution offline akışı | Tugboard kullanıcı olarak bağlantı yokken kritik kayıtları kaybetmeden çalışmak istiyorum. | Job snapshot prefetched; briefing/execution/log durable queue; reconnect idempotent; material conflicts explicit. | mobile-task-center / Tug Ops | P0 | S10 | Full Stack | DEV-033,DEV-034,DEV-035,DEV-089 | T-TUG-013 | Not Started | YES | 13 | H | v46.2
DEV-093 | Task | E21 Tug Operations | Regulatory | Tug regulatory source/applicability review | Regulatory owner olarak tug operasyon limitlerinin kontrollü kaynağını doğrulamak istiyorum. | Flag/class/company/local source ownership assigned; unknown rules remain REVIEW_REQUIRED; no unsupported legal claim. | Regulatory Trace | P0 | S11 | Regulatory Lead | DEV-008,DEV-084,DEV-087 | T-TUG-014 | Not Started | YES | 8 | H | v46.2
DEV-094 | Task | E21 Tug Operations | UAT | Tug role UAT | Tug Master ve operasyon sorumlusu olarak işi talepten kapanışa yardımsız tamamlamak istiyorum. | Intake→assignment→readiness→plan→briefing→execution→log journey meets agreed task success; blocker UX issue=0. | UAT Tug Mode | P0 | S11 | QA/UX/Product | DEV-081:DEV-092 | T-TUG-015 | Not Started | YES | 8 | M | v46.2
DEV-095 | Task | E21 Tug Operations | Pilot | Dual-mode pilot proof | PO olarak bir gemi ve bir römorkörde core ortak altyapı ile iki modun çalıştığını kanıtlamak istiyorum. | 1 ship departure/safety flow + 1 tug job/towage flow; shared crew/PMS/evidence/audit/offline demonstrated; metrics captured. | Pilot | P0 | PILOT-W2 | Product+Pilot Team | DEV-075,DEV-094 | T-TUG-016 | Not Started | YES | 5 | H | v46.2
DEV-096 | Task | E21 Tug Operations | Value | Tug value readout | Yönetim olarak tug mode değerini operasyon süresi, kayıt kalitesi ve readiness görünürlüğü ile görmek istiyorum. | Before/after: job prep time, assignment conflict visibility, evidence completeness, offline success, user adoption; expand/fix decision. | Pilot Value | P0 | PILOT-W4 | Product Owner | DEV-095 | T-TUG-017 | Not Started | YES | 5 | M | v46.2
DEV-097 | Story | E22 Ship Operations 2.0 | Noon Report | Noon Report'u tek girişli günlük operasyon merkezi olarak geliştir | Master/Chief Officer olarak günlük konum, voyage, speed, weather, fuel ve ROB verisini tek kontrollü raporda girmek istiyorum. | Position/voyage/activity/speed/weather/fuel/ROB/master review; data downstream voyage, emissions and dashboards tarafından tekrar kullanılabilir; offline save supported. | noon-report / /api/v1/noon-reports | P0 | S5 | Full Stack | DEV-021,DEV-033 | T-OPS2-001 | Not Started | YES | 13 | H | v46.3 NOZZLE benchmark
DEV-098 | Story | E22 Ship Operations 2.0 | Deck Daily Log | Güverte günlük kayıt defterini dijitalleştir | OOW olarak vardiya/pozisyon/nav status/port-cargo activity/handover kayıtlarını tek akışta tutmak istiyorum. | Watch-period log, navigation status, port/cargo activity, pilot/tug activity, ballast, safety note, handover, officer/master review; audit/offline. | deck-daily-log | P0 | S5 | Full Stack | DEV-097 | T-OPS2-002 | Not Started | YES | 8 | M | v46.3
DEV-099 | Story | E22 Ship Operations 2.0 | Engine Daily Log | Makine günlük kayıt defterini dijitalleştir | Watch engineer olarak engine status/hours/fuel/measurements/alarms/defects/handover kaydetmek istiyorum. | Engine/aux hours, fuel/lube, measurements, alarms, defects, WO link, environmental check, C/E review; offline/audit. | engine-daily-log | P0 | S5 | Full Stack | DEV-052,DEV-097 | T-OPS2-003 | Not Started | YES | 8 | M | v46.3
DEV-100 | Story | E22 Ship Operations 2.0 | Fuel/Bunker/ROB | Fuel, Bunker, BDN ve ROB kayıtlarını birleştir | Master/Chief Engineer olarak fuel consumption, delivery, tank ROB ve BDN kanıtını tek modelde yönetmek istiyorum. | Consumption/delivery/transfer/ROB; fuel type; supplier/BDN; quantity; sulphur/viscosity; discrepancy; compliance/verification/evidence; applicability-aware. | fuel-bunker-log / /api/v1/fuel-bunker-logs | P0 | S6 | Full Stack | DEV-097,DEV-099,DEV-030 | T-OPS2-004 | Not Started | YES | 13 | H | v46.3
DEV-101 | Story | E22 Ship Operations 2.0 | Port Activity / SOF | Port Activity & Statement of Facts kaydı | Chief Officer/Master olarak arrival-pilot-tug-berthing-cargo-departure olaylarını timestamp ve eklerle kaydetmek istiyorum. | Structured event timeline; cargo/draught/tug/pilot/delay; Letter of Protest/evidence; voyage link; finalization; not Port OS. | port-activity-sof / /api/v1/port-activity-sof | P1 | S6 | Full Stack | DEV-097 | T-OPS2-005 | Not Started | YES | 8 | M | v46.3
DEV-102 | Story | E22 Ship Operations 2.0 | Downtime | Operational Downtime / Loss of Hire kaydı | Fleet/Technical olarak duruşu neden, süre, defect/WO/event ve operasyonel etkiyle izlemek istiyorum. | Start/end/duration/cause; defect/WO/event links; operational impact; Loss of Hire candidate; claim evidence; verified closure. | operational-downtime | P1 | S6 | Full Stack | DEV-055,DEV-099 | T-OPS2-006 | Not Started | YES | 8 | M | v46.3
DEV-103 | Story | E10 Technical/PMS | Service Reports | Service & Engineer Report'u WO/equipment ile bağla | Chief Engineer olarak servis/onarım raporunu iş emri ve ekipman tarihçesine bağlamak istiyorum. | Provider/engineer/date/scope/work/parts/tests/defects/recommendations/evidence; verifier; immutable history. | service-engineer-report | P1 | S8 | Full Stack | DEV-055 | T-PMS2-001 | Not Started | YES | 8 | M | v46.3
DEV-104 | Story | E16 Certificate Intelligence | Pre-Survey | Pre-Survey Checklist ve voyage-fit hazırlığı | Superintendent olarak sörvey öncesi hazırlık görevlerini requirement/evidence/due/voyage-fit ile izlemek istiyorum. | Template/items/owner/due/evidence/verification/finding/voyage-fit; unresolved critical item blocks survey readiness. | pre-survey-checklist | P0 | S7 | Full Stack | DEV-060,DEV-061 | T-CERT2-001 | Not Started | YES | 8 | M | v46.3
DEV-105 | Story | E06 Safety & Learning | Risk Assessment | Genel Risk Assessment workspace | Master/HSEQ olarak operasyon/iş bazlı initial/residual risk ve control/barrier setini yönetmek istiyorum. | Hazard/consequence/initial risk/controls/owner/barriers/residual risk/stop-work/approval/ack; traceable to job/WO/event. | risk-assessment | P0 | S7 | Full Stack | DEV-040,DEV-055 | T-RISK2-001 | Not Started | YES | 13 | H | v46.3
DEV-106 | Story | E06 Safety & Learning | Risk Template | Risk Template Library ve revizyon yönetimi | HSEQ olarak fleet-standard risk template'lerini kontrollü yayımlamak ve crew improvement suggestion almak istiyorum. | Work type/scope/revision/effective date/hazards/default controls/barriers/owner/status/suggestions/source refs; superseded versions retained. | risk-template-library | P0 | S7 | Full Stack | DEV-105 | T-RISK2-002 | Not Started | YES | 8 | M | v46.3
DEV-107 | Story | E06 Safety & Learning | High-Risk Work | Fleet High-Risk Work exception görünümü | DPA/HSEQ olarak tüm filodaki yüksek riskli işleri risk/permit/barrier/crew/equipment readiness ile görmek istiyorum. | Fleet filter; risk/permit/barrier/crew/equipment state; owner/due; Why drill-down; no score hides critical blocker. | high-risk-work | P1 | S8 | Frontend+Backend | DEV-105,DEV-106 | T-RISK2-003 | Not Started | YES | 8 | M | v46.3
DEV-108 | Story | E10 Technical/PMS | Measurements | PMS measurement point modelini güçlendir | Technical olarak RPM/pressure/temp/condition readings ile threshold-based maintenance tetiklemek istiyorum. | Measurement definitions, unit/range, source/manual-device, reading history, parent/sub counter propagation, threshold trigger, evidence. | running-hours-meter + condition-monitoring | P1 | S8 | Backend+Frontend | DEV-052,DEV-054 | T-PMS2-002 | Not Started | YES | 8 | M | NOZZLE benchmark strengthen
DEV-109 | Story | E10 Technical/PMS | Postponement | Work Order postponement governance | Chief Engineer/Tech Manager olarak WO ertelemesini gerekçe/onay/yeni due/readiness impact ile kontrollü yapmak istiyorum. | Postpone request; reason; authority; risk review; new due; criticality; readiness recalculation; audit; max extension policy. | work-order-detail | P0 | S8 | Full Stack | DEV-055,DEV-105 | T-PMS2-003 | Not Started | YES | 8 | H | v46.3
DEV-110 | Story | E19 Technical Supply | Critical Spares | Low-stock ve teknik otomatik requisition | Chief Engineer olarak critical spare min seviyeye inince kontrollü requisition başlatmak istiyorum. | Min/max; current stock; WO/equipment criticality; low-stock alert; proposed requisition; human approval; no full procurement workflow. | critical-spares + technical-requisition | P0 | S8 | Full Stack | DEV-057 | T-SUP2-001 | Not Started | YES | 8 | M | ERP boundary preserved
DEV-111 | Story | E10 Technical/PMS | Drydock | Drydock-cert-survey-WorkOrder bağını güçlendir | Technical Superintendent olarak drydock scope'u WO/defect/certificate/survey ile planlamak istiyorum. | Drydock timeline; scope items; WO/defect/survey/cert links; readiness and evidence; supplier/budget remain external/integration-only. | drydock-planning | P1 | S9 | Full Stack | DEV-055,DEV-104 | T-PMS2-004 | Not Started | NO | 8 | M | v46.3 strengthen
DEV-112 | Story | E16 Certificate Intelligence | Survey Calendar | Survey Planner'a fleet calendar ve voyage-aware fit ekle | Superintendent olarak survey/certificate renewal'ı voyage takvimiyle çakıştırmadan planlamak istiyorum. | Fleet calendar; survey window; voyage/port fit; pre-survey checklist; class/flag coordination; CONDITIONAL/NOT_FIT states. | survey-planner | P1 | S7 | Full Stack | DEV-104 | T-CERT2-002 | Not Started | YES | 8 | M | NOZZLE benchmark strengthen
DEV-113 | Story | E17 Assurance & Audit | SIRE 2.0 | SIRE 2.0 inspection import ve offline evidence | Tanker assurance olarak inspection items/findings/evidence'i kontrollü içe alıp offline saha doğrulamak istiyorum. | Versioned import mapping; no blind overwrite; offline photo/video evidence; finding/action trace; tanker-only applicability. | industry-assurance + audit-ready | P1 | S10 | Full Stack | DEV-063,DEV-031 | T-ASS2-001 | Not Started | NO | 13 | H | v46.3 tanker package
DEV-114 | Story | E08 Controlled Knowledge | Document Compare | Doküman side-by-side version compare ve security controls | Document Controller olarak iki revizyonu karşılaştırmak ve hassas dokümanda download/print politikasını uygulamak istiyorum. | Version diff; approval history; download/print policy; ISPS sensitive document ACL; acknowledgement retained. | controlled-knowledge | P1 | S9 | Full Stack | DEV-045,DEV-006 | T-DOC2-001 | Not Started | NO | 8 | M | v46.3 strengthen
DEV-115 | Task | E20 Production Hardening | Benchmark Regression | v46.3 competitor-delta regression pack | QA olarak 11 yeni ekran ve güçlendirilen PMS/assurance akışlarında v46.2 non-regression kanıtı istiyorum. | 196 screen inventory; 2316 field trace; 11 new-screen E2E; no tug/applicability/readiness regression; old URLs/IDs stable unless controlled change. | RTM + Test Pack | P0 | S10 | QA/BA | DEV-097:DEV-114 | T-V463-001 | Not Started | YES | 13 | H | v46.3 controlled candidate
DEV-116 | Task | E20 Production Hardening | ERP Boundary | ERP scope boundary integration contracts | Architect olarak finance/payroll/full procurement/warehouse/chartering'in ürün içine sızmamasını istiyorum. | Explicit OUT list; integration-only contracts; technical requisition/critical spares boundary; no accidental PO/AP/AR/payroll tables. | Architecture / API | P0 | S0 | Solution Architect | DEV-004 | T-V463-002 | Not Started | YES | 5 | M | Strategic guardrail
DEV-117 | Task | E20 Production Hardening | Class Approval | PMS type approval roadmap | Product/Technical olarak DNV/ClassNK/Türk Loydu gap analizini ve kanıt planını görmek istiyorum. | Target class; applicable approval scheme; gap list; required PMS features/test evidence; owner/timeline; no certification claim before award. | Certification Roadmap | P1 | S11 | Product+Technical | DEV-103,DEV-108,DEV-109 | T-V463-003 | Not Started | NO | 5 | M | NOZZLE proof gap
DEV-118 | Task | E20 Production Hardening | Security Certification | ISO 27001/27701 readiness roadmap | Security/Product olarak enterprise certification hazırlık backlog'unu oluşturmak istiyorum. | ISMS/PIMS scope, controls/evidence owners, audit readiness, provider/tenant/data boundaries; roadmap approved. | Security Roadmap | P1 | S11 | Security/Product | DEV-006 | T-V463-004 | Not Started | NO | 5 | M | Commercial proof
DEV-119 | Task | E21 Tug Operations | Differentiator Demo | Römorkör end-to-end buyer demo'sunu v46.3'e göre güçlendir | Presales/PO olarak tug job'dan evidence/history'ye farklılaştırıcı akışı 10 dakikada göstermek istiyorum. | Intake→assignment→BP/crew/equipment readiness→plan→RA/briefing→Master release→execution→evidence; Why visible. | Tug Demo Journey | P0 | S10 | Product+UX | DEV-081:DEV-092,DEV-105 | T-V463-005 | Not Started | YES | 5 | M | Core wedge
DEV-120 | Task | E22 Ship Operations 2.0 | Ship Demo | Gemi operasyon buyer demo'su | Presales/PO olarak Departure→Noon/Daily Log→Fuel/BDN→SOF→Downtime→Readiness akışını göstermek istiyorum. | Single-entry reuse visible; compliance/technical links; no duplicate entry; Why/readiness/evidence shown. | Ship Demo Journey | P0 | S10 | Product+UX | DEV-097:DEV-102 | T-V463-006 | Not Started | YES | 5 | M | Close ship-ops gap
DEV-121 | Task | E20 Production Hardening | Pilot Proof | v46.3 ship+tug pilot proof metrics | PO olarak rakip analizinden eklenen işlevlerin sahada değerini kanıtlamak istiyorum. | 1 ship + 1 tug; time-to-complete; duplicate-entry reduction; evidence completeness; readiness accuracy; offline success; user adoption; signed UAT. | Pilot Metrics | P0 | PILOT-W4 | Product+Pilot | DEV-115,DEV-119,DEV-120 | T-V463-007 | Not Started | YES | 8 | H | Feature list değil proof

## Sprint Plan
Sprint | Phase | Start | End | Primary Outcome | Exit Gate | v46.2 Dual-Mode Milestone | Proof
S0 | Sprint 0 / Freeze | 2026-10-05 | 2026-10-16 | Spec/architecture/security/data/trace/environment freeze | Sprint 0 Gate PASS | S5-S6 | Tug context + job intake/board
S1 | Foundation | 2026-10-19 | 2026-10-30 | Identity, tenant isolation, RBAC, audit, secure files | Security/tenant baseline pass | S7 | Assignment + readiness + crew/equipment
S2 | Foundation | 2026-11-02 | 2026-11-13 | Vessel/role context, role-first shell, Today, Why foundation | Role UX shell UAT | S8 | Towage plan + risk/briefing
S3 | Foundation | 2026-11-16 | 2026-11-27 | Requirement/applicability/control/evidence/verification/decision E2E | Core trace chain E2E pass | S9 | Towage execution + log
S4 | Foundation | 2026-11-30 | 2026-12-11 | Offline queue/sync/conflict + notifications + health | Offline chaos baseline pass | S10 | Offline/history hardening
S5 | Pilot Vertical Slice | 2026-12-14 | 2026-12-25 | Vessel onboarding + applicability/control generation | Onboarding/applicability SME review | S11 | Tug UAT + regulatory review
S6 | Pilot Vertical Slice | 2026-12-28 | 2027-01-08 | Certificate intelligence + renewal + OCR assist | Certificate/OCR validation | Pilot | 1 ship + 1 tug dual-mode proof
S7 | Pilot Vertical Slice | 2027-01-11 | 2027-01-22 | Crew roster/certificates/competence/safe manning | Crew eligibility UAT
S8 | Pilot Vertical Slice | 2027-01-25 | 2027-02-05 | PMS/WO/critical defect + offline WO | Technical pilot flow pass
S9 | Pilot Vertical Slice | 2027-02-08 | 2027-02-19 | Departure/Master sign-off + safety event + voice draft | Master/safety journeys pass
S10 | Pilot Vertical Slice | 2027-02-22 | 2027-03-05 | Audit/data trust/offline/security/performance hardening | Pre-pilot hardening gates
S11 | Pilot Vertical Slice | 2027-03-08 | 2027-03-19 | Migration/DR/pilot metrics/regulatory/UAT/go-no-go | Pilot GO
PILOT-W1 | 30-Day Design Partner Pilot | 2027-03-22 | 2027-03-26 | Today/Vessel/Certificates/Crew | Week 1 trace proof
PILOT-W2 | 30-Day Design Partner Pilot | 2027-03-29 | 2027-04-02 | PMS/Defect/Departure/Offline | Week 2 onboard proof
PILOT-W3 | 30-Day Design Partner Pilot | 2027-04-05 | 2027-04-09 | Safety/Event/Evidence/AI | Week 3 audit/AI proof
PILOT-W4 | 30-Day Design Partner Pilot | 2027-04-12 | 2027-04-16 | Assurance/UAT/Value Readout | Go/No-Go/Expand

## Dashboard
POSEIDON v46.2 — GEMİ + RÖMORKÖR Development Dashboard
Metric | Value | Sprint | Items
Total backlog | 96 | S0 | 12
P0 items | 87 | S1 | 7
Pilot-gate items | 95 | S2 | 6
Total story points | 760 | S3 | 7
Done items | 0 | S4 | 6
|  | S5 | 4
|  | S6 | 4
|  | S7 | 5
|  | S8 | 6
|  | S9 | 6
|  | S10 | 5
|  | S11 | 7
|  | PILOT-W1 | 1
|  | PILOT-W2 | 1
|  | PILOT-W3 | 1
|  | PILOT-W4 | 1

## DoR DoD Gates
Section | Rule
Definition of Ready | User/business outcome clear; role/context defined; acceptance criteria testable; design state identified; screen/API/entity/trace known; security/offline/regulatory impact assessed; dependencies resolved.
Definition of Done | Acceptance passed; code review; automated tests; design conformance; authorization/audit verified; offline covered where relevant; trace/regulatory impact updated; docs current; no unresolved critical/high issue in release scope.
Pilot Gate | Security, tenant isolation, regulatory SME review, offline chaos, DR restore, UAT, data reconciliation, traceability and support readiness PASS.
Production Gate | All critical E2E PASS; tenant leakage 0; critical audit coverage 100%; backup/restore and security tests pass; no autonomous high-risk AI decision; regulatory source ownership current.

## RACI
Workstream | PO | BA | Architect | Backend | Frontend | QA | DevOps | Regulatory SME | UX | Pilot Customer
Scope / Priority | A | R | C | I | I | C | I | C | C | C
Architecture / ADR | C | I | A/R | C | C | C | C | I | I | I
Regulatory applicability | A | R | C | I | I | C | I | A/R | I | C
Security / tenancy | I | I | A | R | C | C | R | I | I | I
UX / role journeys | A | C | C | C | R | C | I | I | A/R | C
Offline / sync | C | C | A | R | R | R | C | I | C | C
Pilot data migration | A | R | C | R | I | R | C | C | I | C
UAT / Pilot | A | R | C | C | C | A/R | C | C | R | R
Release gate | A | C | C | C | C | R | R | C | C | I

## RAID
ID | Type | Description | Impact | Mitigation / Decision | Owner | Status
R-01 | Risk | Authoritative regulatory interpretation remains incomplete for some instruments/flag/class overlays | High | Regulatory source register + SME/flag/class review; ambiguity stays REVIEW_REQUIRED | Regulatory Lead | Open
R-02 | Risk | Scope expands beyond pilot vertical slice | High | No new generic module without validated pilot journey; CR approval required | Product Owner | Open
R-03 | Risk | Offline conflicts corrupt material shipboard records | High | Durable queue + idempotency + versioning + explicit human conflict resolution | Architect | Open
R-04 | Risk | AI extraction/draft produces unsupported facts | High | Source trace/confidence/user confirmation/golden-set evaluation; no autonomous submission | AI Lead | Open
R-05 | Risk | Tenant data leakage | Critical | Server-side authorization + automated cross-tenant regression + pre-pilot security gate | Security | Open
R-06 | Risk | Pilot data import quality is poor | Medium | Validation/reject/reconciliation report and customer sign-off | Implementation | Open
A-01 | Assumption | Pilot design partner can provide masked real documents and operational users | High | Confirm before S6; fallback synthetic golden set only for development, not value proof | Product Owner | To Confirm
D-01 | Decision | Architecture remains modular-monolith-first | Medium | Avoid premature distributed complexity; split only with proven scale/operational need | Architect | Accepted
D-02 | Decision | 172 screens are capability depth, not navigation depth | High | Role-first Today + contextual menus; full screen search only for authorized power users | PO/UX | Accepted
D-03 | Decision | Readiness uses categorical state, not one averaged safety score | High | READY/CONDITIONAL/NOT_READY/REVIEW_REQUIRED + evidence completeness as secondary metric | PO/Regulatory | Accepted
D-04 | Decision | Primary product scope is Gemi + Römorkör | High | Fleet/company remains management context; Tug Mode is first-class, not profile-only | PO | Accepted
D-05 | Decision | Tug-to-job assignment is in scope | High | Port traffic/berth/resource management remains out | PO/Operations | Accepted
R-09 | Risk | Tug-specific regulatory sources are not fully validated | High | Source register + flag/class/company/local SME validation; unknown state remains REVIEW_REQUIRED | Regulatory Lead | Open

## v46.2 Scope
POSEIDON v46.2 Development Scope | Gemi + Römorkör dual-mode
Primary scope | Ship management + Tug operations/safety management
Fleet/company | Management context only
Port boundary | No port/terminal/berth/port-traffic management
Tug included | Job intake, job board, own tug assignment, readiness, towage plan/risk, execution, equipment/crew, log/history
Pilot | Minimum one ship + one tug / mixed operator
Controlled screens | 185
Field contracts | 2126

## Tug Ops v46.2
ID | Type | Epic | Feature | Title | User Story | Acceptance Criteria | Screen / API | Priority | Sprint | Owner Role | Dependencies | Test Trace | Status | Pilot Gate | Estimate SP | Risk | Notes
DEV-080 | Story | E21 Tug Operations | Tug Context | Römorkör mode context ve profile root | Römorkör Operasyon Sorumlusu olarak römorkörün operasyonel profile/role contextini görmek istiyorum. | Tug profile bollard pull/type/equipment context + role lens; Ship Mode screens remain hidden unless cross-mode role. | tug-command / /api/v1/tug-command | P0 | S5 | Full Stack | DEV-020,DEV-022 | T-TUG-001 | Not Started | YES | 8 | M | v46.2
DEV-081 | Story | E21 Tug Operations | Job Intake | Römorkör iş talebi kaydı | Operasyon sorumlusu olarak yeni römorkaj işini assisted vessel, zaman, alan, BP ve özel gereksinimle açmak istiyorum. | Job ID; assisted vessel; job type; time window; area; required tug count/BP; priority; owner; audited create. | tug-job-intake / /api/v1/tug-jobs | P0 | S6 | Full Stack | DEV-080 | T-TUG-002 | Not Started | YES | 8 | M | v46.2
DEV-082 | Story | E21 Tug Operations | Job Board | Kısa ve sık römorkör iş panosu | Operasyon sorumlusu olarak gün içi işleri zaman ve readiness ile görmek istiyorum. | Job board shows planned window, assigned tugs, BP, readiness, conflict, priority and next action. | tug-job-board | P0 | S6 | Frontend+Backend | DEV-081 | T-TUG-003 | Not Started | YES | 8 | M | v46.2
DEV-083 | Story | E21 Tug Operations | Assignment | Römorkör atama ve çakışma kontrolü | Operasyon sorumlusu olarak işi uygun römorköre atarken overlap, crew, equipment, PMS ve certificate durumunu görmek istiyorum. | Assignment checks time overlap + crew/equipment/PMS/cert; shore proposes; Master/Tug Master acknowledgement preserved. | tug-assignment / /api/v1/tug-assignments | P0 | S7 | Full Stack | DEV-050,DEV-055,DEV-082 | T-TUG-004 | Not Started | YES | 13 | H | v46.2
DEV-084 | Story | E21 Tug Operations | Readiness | Römorkör operasyon readiness gate | Master/Tug Master olarak işe çıkmadan crew, equipment, PMS, certificate, comms, weather ve BP margin görmek istiyorum. | READY/CONDITIONAL/NOT_READY/REVIEW_REQUIRED; critical blocker cannot be averaged; Master decision and reason retained. | tug-readiness / /api/v1/tug-readiness | P0 | S7 | Full Stack | DEV-083 | T-TUG-005 | Not Started | YES | 13 | H | v46.2
DEV-085 | Story | E21 Tug Operations | Equipment Readiness | Tow equipment readiness | Chief Engineer olarak winch, tow hook, towline, emergency release, FiFi ve critical defects durumunu görmek istiyorum. | SWL/test/condition/PMS/certificate evidence; NOT_READY on critical failure; evidence/verification trace. | tug-equipment-readiness | P0 | S7 | Full Stack | DEV-052,DEV-055 | T-TUG-006 | Not Started | YES | 8 | H | v46.2
DEV-086 | Story | E21 Tug Operations | Crew Readiness | Römorkör crew/towage competence readiness | Master/Crewing olarak minimum manning, credential, towage competence, familiarization ve work/rest durumunu görmek istiyorum. | Shared crew engine + tug-specific towage competence; positive readiness blocked by missing/unverified credential/competence. | tug-crew-readiness | P0 | S7 | Full Stack | DEV-048,DEV-050 | T-TUG-007 | Not Started | YES | 8 | H | v46.2
DEV-087 | Story | E21 Tug Operations | Towage Plan | Römorkaj operasyon planı | Master/Tug Master olarak çekme konfigürasyonu, towline, BP, limitler, communication ve contingency planını hazırlamak istiyorum. | Plan has tug roles, configuration, limits, communication, emergency release, contingency, snap-back controls and approval state. | towage-plan / /api/v1/towage-plans | P0 | S8 | Full Stack | DEV-084,DEV-085 | T-TUG-008 | Not Started | YES | 13 | H | v46.2
DEV-088 | Story | E21 Tug Operations | Risk & Briefing | Römorkaj risk ve brifing | Master/Tug Master olarak weather/current/visibility/hazards/barriers/stop-work koşullarını ekip ile teyit etmek istiyorum. | Risk state + preventive/mitigating barriers + stop-work + emergency + participants acknowledgement; incomplete briefing blocks READY. | towage-risk-briefing | P0 | S8 | Full Stack | DEV-087 | T-TUG-009 | Not Started | YES | 8 | H | v46.2
DEV-089 | Story | E21 Tug Operations | Execution | Römorkaj operasyon yürütme | Master/Tug Master olarak start/suspend/resume/abort/complete ve operasyon kanıtını kaydetmek istiyorum. | Timeline, towline times, max load, comms, weather, events, Master decision, evidence, verification; shore/AI cannot start/abort operation. | towage-execution / /api/v1/towage-executions | P0 | S9 | Full Stack | DEV-088,DEV-031 | T-TUG-010 | Not Started | YES | 13 | H | v46.2
DEV-090 | Story | E21 Tug Operations | Daily Log | Römorkör günlük defteri | Master olarak vardiya/gün sonunda iş, runtime, fuel, defect, safety event ve özet kaydı yapmak istiyorum. | Daily log works offline; job links and meter values reconcile; Master review + sync state visible. | tug-daily-log | P1 | S9 | Full Stack | DEV-033,DEV-089 | T-TUG-011 | Not Started | YES | 8 | M | v46.2
DEV-091 | Story | E21 Tug Operations | History | Römorkör operasyon geçmişi | Operasyon/DPA olarak geçmiş işi gemi, tip, süre, Master, sonuç ve evidence durumuyla aramak istiyorum. | History filterable by tug/job/vessel/date/outcome; no silent deletion; trace to evidence/event. | tug-operation-history | P1 | S10 | Full Stack | DEV-089 | T-TUG-012 | Not Started | YES | 5 | M | v46.2
DEV-092 | Story | E21 Tug Operations | Offline | Römorkör job/briefing/execution offline akışı | Tugboard kullanıcı olarak bağlantı yokken kritik kayıtları kaybetmeden çalışmak istiyorum. | Job snapshot prefetched; briefing/execution/log durable queue; reconnect idempotent; material conflicts explicit. | mobile-task-center / Tug Ops | P0 | S10 | Full Stack | DEV-033,DEV-034,DEV-035,DEV-089 | T-TUG-013 | Not Started | YES | 13 | H | v46.2
DEV-093 | Task | E21 Tug Operations | Regulatory | Tug regulatory source/applicability review | Regulatory owner olarak tug operasyon limitlerinin kontrollü kaynağını doğrulamak istiyorum. | Flag/class/company/local source ownership assigned; unknown rules remain REVIEW_REQUIRED; no unsupported legal claim. | Regulatory Trace | P0 | S11 | Regulatory Lead | DEV-008,DEV-084,DEV-087 | T-TUG-014 | Not Started | YES | 8 | H | v46.2
DEV-094 | Task | E21 Tug Operations | UAT | Tug role UAT | Tug Master ve operasyon sorumlusu olarak işi talepten kapanışa yardımsız tamamlamak istiyorum. | Intake→assignment→readiness→plan→briefing→execution→log journey meets agreed task success; blocker UX issue=0. | UAT Tug Mode | P0 | S11 | QA/UX/Product | DEV-081:DEV-092 | T-TUG-015 | Not Started | YES | 8 | M | v46.2
DEV-095 | Task | E21 Tug Operations | Pilot | Dual-mode pilot proof | PO olarak bir gemi ve bir römorkörde core ortak altyapı ile iki modun çalıştığını kanıtlamak istiyorum. | 1 ship departure/safety flow + 1 tug job/towage flow; shared crew/PMS/evidence/audit/offline demonstrated; metrics captured. | Pilot | P0 | PILOT-W2 | Product+Pilot Team | DEV-075,DEV-094 | T-TUG-016 | Not Started | YES | 5 | H | v46.2
DEV-096 | Task | E21 Tug Operations | Value | Tug value readout | Yönetim olarak tug mode değerini operasyon süresi, kayıt kalitesi ve readiness görünürlüğü ile görmek istiyorum. | Before/after: job prep time, assignment conflict visibility, evidence completeness, offline success, user adoption; expand/fix decision. | Pilot Value | P0 | PILOT-W4 | Product Owner | DEV-095 | T-TUG-017 | Not Started | YES | 5 | M | v46.2

## v46.3 Scope
POSEIDON v46.3 Development Scope | Controlled Candidate / NOZZLE benchmark delta
Parent baseline | v46.2 — 185 screens / 2.126 field contracts
Primary scope | Ship + Tug Safe Operations, Compliance & Readiness Platform
Current candidate inventory | 196 screens / 2.316 field contracts
Ship delta | Noon, Deck/Engine Daily Logs, Fuel/Bunker/ROB, Port Activity/SOF, Operational Downtime
PMS/Assurance delta | Service/Engineer Report, Pre-Survey Checklist; Job Pool/Drydock/Survey/Spare flows strengthened
Safety delta | General RA, Risk Template Library, Fleet High-Risk Work; barrier/effectiveness retained
Tug | 13-screen first-class Tug lifecycle unchanged and remains strategic wedge
ERP boundary | Finance/payroll/full procurement/RFQ/PO/warehouse/chartering OUT or integration-only
Port boundary | Port/terminal/berth/VTS management OUT; vessel/tug own operational context IN
Pilot | Minimum 1 ship + 1 tug; v46.3 new ship-ops + existing tug differentiator both demonstrated

## v46.3 Sprint Plan
Sprint | Phase | Primary Outcome | v46.3 Increment | Exit Gate | Primary New IDs
S0 | Candidate Freeze | Scope/trace/architecture/backlog/test freeze | ERP boundary + 196/2316 trace + benchmark delta | v46.3 Candidate Gate PASS | DEV-115,116
S1 | Foundation | Identity/tenant/RBAC/audit/files | No benchmark-specific scope; foundation retained | Security/tenant pass | Existing S1
S2 | Foundation | Role shell / Today / Why | 196-screen navigation/projection compatibility | Role UX pass | Existing S2
S3 | Foundation | Applicability→Control→Evidence→Decision | NOZZLE additions reuse same regulatory/evidence core | Trace E2E pass | Existing S3
S4 | Foundation | Offline queue/sync/conflict | Daily logs / inspections / tug flows share offline contract | Offline chaos pass | Existing S4
S5 | Ship Ops 2.0 | Voyage/Noon/Daily logs | Noon + Deck + Engine | Ship daily ops UAT | 097-099
S6 | Ship Ops 2.0 | Fuel/BDN/SOF/Downtime | Fuel/Bunker/ROB + Port Activity/SOF + Downtime | Ship ops vertical slice | 100-102
S7 | Crew/Risk/Certificate | Crew eligibility + RA + pre-survey | Risk workspace/templates + Pre-Survey + Survey Planner strengthen | Safety/assurance UAT | 104-106,112
S8 | PMS 2.0 | Technical reliability depth | Service report + measurements + postponement + critical spares | Technical UAT | 103,108-110
S9 | PMS/Knowledge/Tug | Drydock/doc controls + Tug planning | Drydock strengthen + doc compare + Tug intake/assignment/readiness/plan | Mixed-mode UAT | 111,114 + Tug
S10 | Tug/Assurance/Regression | Towage execution + SIRE + benchmark regression | Tug end-to-end + SIRE + ship/tug demo journeys | Pre-pilot hardening | 113,115,119,120
S11 | Certification/Pilot Gate | Roadmaps + migration/DR/UAT | Class/ISO roadmaps + final pilot prep | Pilot GO | 117,118
PILOT | 30-Day Design Partner Pilot | 1 ship + 1 tug real proof | New ship ops + tug differentiators + readiness/applicability metrics | Signed UAT / Expand-Fix-NoGo | 121

## v46.3 Change Set
ID | Capability | Decision | Priority | Sprint | Screen | Acceptance Summary | Source / Rationale
V463-01 | Noon Report | ADD | P0 | S5 | noon-report | Single-entry daily operational hub, offline + downstream reuse | NOZZLE Operations benchmark
V463-02 | Deck Daily Log | ADD | P0 | S5 | deck-daily-log | Watch/nav/port/cargo/handover | NOZZLE Operations benchmark
V463-03 | Engine Daily Log | ADD | P0 | S5 | engine-daily-log | Hours/fuel/measurements/alarms/defects/handover | NOZZLE Operations benchmark
V463-04 | Fuel/Bunker/ROB/BDN | ADD | P0 | S6 | fuel-bunker-log | Consumption/delivery/ROB/compliance/evidence | NOZZLE Operations benchmark
V463-05 | Port Activity / SOF | ADD | P1 | S6 | port-activity-sof | Timestamped vessel activity; not Port OS | NOZZLE Operations benchmark
V463-06 | Operational Downtime | ADD | P1 | S6 | operational-downtime | Defect/WO/event causal trace + claim evidence | NOZZLE Loss of Hire benchmark
V463-07 | Service Engineer Report | ADD | P1 | S8 | service-engineer-report | WO/equipment service evidence | NOZZLE PMS benchmark
V463-08 | Pre-Survey Checklist | ADD | P0 | S7 | pre-survey-checklist | Survey preparation + voyage fit + evidence | NOZZLE Certificate benchmark
V463-09 | Risk Assessment | ADD | P0 | S7 | risk-assessment | Point-of-work RA + barriers | NOZZLE RISQ benchmark
V463-10 | Risk Template Library | ADD | P0 | S7 | risk-template-library | Fleet standard + version + crew improvement | NOZZLE RISQ benchmark
V463-11 | Fleet High-Risk Work | ADD | P1 | S8 | high-risk-work | Fleet exception view | NOZZLE RISQ benchmark
V463-B1 | Finance/Payroll/Full Procurement/Warehouse/Chartering | EXCLUDE/INTEGRATE | P0 | S0 | — | Explicit architectural boundary | Do not copy maritime ERP breadth