POSEIDON v46.3

Release, Version ve Change Control Standardı

Requirement değişikliğinden controlled release'e

| Konu | Kontrollü Değer |
| --- | --- |
| Amaç | v46.3 sonrası kontrolsüz dosya/requirement çoğalmasını engellemek |
| Değişiklik ilkesi | Change Control / MOC; sessiz overwrite yok |
| Trace ilkesi | Requirement → Screen → Field → API/Entity → Test birlikte etkilenir |
| Versiyon ilkesi | Draft ≠ Candidate ≠ Final ≠ Released ≠ Superseded |
| Acil değişiklik | Expedited olabilir; audit/retrospective zorunludur |

# 1. Version modeli

| Katman | Örnek | Kural |
| --- | --- | --- |
| Product baseline | v46.3 | Scope ve controlled artifacts |
| Release | R1.0.0 | Production deploy edilen yazılım |
| Hotfix | R1.0.1 | Backward-compatible urgent defect fix |
| Minor | R1.1.0 | Compatible feature/change |
| Major | R2.0.0 | Breaking contract/data/behavior |
| Document revision | Doc Rev 1.2 | Product versiondan bağımsız editorial/control revision |

# 2. Change sınıfları

| Class | Örnek | Minimum approval |
| --- | --- | --- |
| C0 Editorial | Yazım, açıklama, non-functional text | Document owner |
| C1 Low functional | Non-critical UI/validation | PO + QA |
| C2 Material functional | Workflow/state/role/data change | PO + BA + Architect + QA |
| C3 Regulatory/Safety | Applicability/readiness/crew/PMS critical rule | PO + Regulatory/Marine/Tug SME + QA |
| C4 Breaking/Platform | Schema/API/security/offline/tenant boundary | Product Council + Architecture + Security + QA |

# 3. Change Request zorunlu alanları

Change ID

Problem/trigger

Source/customer/regulatory reference

Affected role/mode/context

Current behavior

Proposed behavior

Reason/value

Safety/regulatory impact

Data/API/offline/security impact

Migration/backward compatibility

Test plan

Rollout/rollback

Owner/approvers

# 4. Impact Analyzer

| Kontrol | Soru |
| --- | --- |
| Scope | Ship/Tug/Shared core/Out-of-scope sınırı etkileniyor mu? |
| Regulatory | Source/version/effective date veya applicability rule değişiyor mu? |
| UX | Screen/field/role visibility/state/action değişiyor mu? |
| Data | Entity/schema/history/retention/provenance etkisi? |
| API | Contract/event/version/backward compatibility etkisi? |
| Offline | Queued command/conflict/merge davranışı etkisi? |
| Security/Privacy | Permission/PII/provider/logging etkisi? |
| AI | Prompt/model/tool/authority/evaluation etkisi? |
| Test | Golden test/regression/UAT/pilot tekrar gerekir mi? |
| Docs | Master/PRD/Trace/Prototype/Backlog/Runbook değişiyor mu? |

# 5. State machine

DRAFT → ANALYSIS → IMPACT_REVIEW → APPROVED → IMPLEMENTING → VERIFYING → RELEASE_READY → RELEASED → EFFECTIVENESS_REVIEW → CLOSED

REJECTED / DEFERRED / CANCELLED kontrollü state'lerdir; RELEASED kayıt silinmez.

# 6. Definition of Ready

Problem ve acceptance criteria net

Affected artifacts listesi hazır

Regulatory/safety impact reviewed

Design/data/API direction approved

Test trace tanımlı

Owner/dependency/rollout known

# 7. Definition of Done

Code/contract updated

Automated + functional + regulatory tests pass

Security/offline/audit checks complete

Traceability current

Documentation current

Release note prepared

Migration/rollback tested if applicable

# 8. Emergency change

P0 production/safety incident için minimum gerekli değişiklik hızlı uygulanabilir.

Approver ve rollback owner önceden atanır; evidence/correlation/log korunur.

En geç sonraki iş günü retrospective change record tamamlanır.

Emergency path regulatory/source doğrulamasını atlama gerekçesi değildir.